| Name | Evictions / Litani TF | Meeting Date | 10 April 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 15.00 |
| Co-Chairs | Hussein Salem (MoSA) – Josep Zapater (UNHCR) | Meeting Duration | 2:15 hour |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |
| Purpose of Meeting | Review current Evictions / Litani situation and agree on collective action |

Meeting

Meeting agenda

- Follow up on action points from last meeting

- Litani situation: general approach and timelines

- Relocation modalities

- Assessment modalities

- Next steps

Summary of discussions and decisions

- A draft action plan for assessment – relocation relating to the Litani river situation was presented. It needs to be finished Friday, for sharing with Snr Management in Beirut.

- Full assessments and plans for the pilot relocation of three sites need to be ready by Tuesday 16th April next week, for discussion Wednesday at the Task Force. The relocation needs to happen in no more than a month’s time.

Action points – Zahle situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Discuss with Zahle Mayor the possibility to undertake joint technical assessments of sites close to the Litani river, without presence of the Municipal police | MOIM | 10 April 10:00 |  |
| Continue protection assessment of sites who have received eviction notices or pressures and notify MOIM and MOSA. | Fawad | Continuous |  |
| Prepare a letter to Mayor of Zahle documenting the cases of municipal police visiting sites with requests linked to the Litani situation or invitations or intimations to relocate | Protection | 12 April COB |  |

Action points – Litani situation

| Send comments to narrative of action plan | All | 11 April COB |  |
| --- | --- | --- | --- |
| Formally notify families of the need to relocate, and organized as necessary go and see visits | MOSA | 11 April COB |  |
| Incorporate comments and share with Beirut Snr Management (MOSA and UNHCR) | Raffaella and Hussein | 12 April COB |  |
| Send comments to Protection on 1) Indicators for household assessment pre-relocation, 2) Counselling lines for refugees (priority for the household assessment: first Excel document) | Sector coordinators | 11 April COB |  |
| Finalize household assessment | Protection | 16 April COB |  |
| Liaise with notary, judge and landlord to ensure that refugees get a written, fair lease agreement | MOSA | ASAP |  |
| Ensure approval of new tents for spontaneous relocation | MOSA and MOIM | Ongoing |  |
| Prepare draft SOPs for use of cash assistance for the Litani situation | Basic Assistance | 16 April COB |  |
| Prepare full action plan for site preparation for the new sites | WASH and Shelter | 16 April COB |  |
| Start WASH technical assessment for sites within 200 m. of the Litani river | WASH sector | 17 April field work starts |  |
| Finalize WASH technical assessment for sites within 200 m. of the Litani river | WASH sector | In time for the 2nd of May review meeting |  |

Next meeting

- Wednesday 17 April 14:30 at UNHCR Zahle, to review the above actions and adjust plans as necessary.

# Text boxes

Evictions / Litani  TF – Minutes of Meeting