## IS-Coordination
2022 LCRP Food Security & Agriculture Workplan - Sector Coordination / Inter-Sector priorities
2022 Timeline
Link to IS Priority/Mainstreaming Area Or link to IS priority | Key Priorities | Main Actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners (optional) | Additional Comments | Status
Coordination | Sector Coordination Efforts | Maintain coordination and communication with other Food Security & Agriculture Sector coordination mechanisms at the regional-level (North, Akkar, Bekaa, BML-South) | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | Regional Food Security & Agriculture Sector Co-coordinators (WFP) |  | Ongoing
|  | Maintain coordination and communication with Core Group through regular and ad-hoc meetings | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | Core Group Members |  | Ongoing
|  | Maintain coordination and communication with partners, provide bilateral guidance and support and linkages to other sectors where needed, engage partners at all level in strategic and operational discussions, including support to avoid duplication of assistance, provide technical guidance on food security, in-kind food assistance, agricultural livelihood, targeting and harmonization of transfer values | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | LCRP partners |  | Ongoing
|  | Maintain coordination and communication with other frameworks coordination mechanisms (e.g. Emergency Response Plan) to ensure complementariety of interventions, reduce overlaps and improve overall humanitarian and development response. This includes coordination around cash-related activities, thematic discussions, assessments etc. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | Sector's lead agencies, Inter-Agency Team (LCRP), EOC (ERP) and Strategic Task Force on Cash, ACTED (as co-chair of the ERP) |  | Ongoing
|  | Ensure ActivityInfo, Service Mapping, RAIS and other reporting/information-sharing platforms are utilised, updated and populated. This includes potential new Deduplication Platform for the Food Security & Agriculture Sector (details TBC) | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | Food Security & Agriculture Sector Information Management Officer and LCRP Info Mgmt Team |  | Ongoing
|  | Maintain Sector webpage up-to-date by uploading WG meeting minutes, guidance, presentations, reports, assessments etc. This also includes ensuring dashboards include latest data/information as reported by Sector partners | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
|  | Ensure cross attendance and participation in other sector's working groups and provide relevant Food Security & Agriculture updates | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | Other Sectors, Inter-Agency Working Group |  | Ongoing
|  | Keep monitoring of the key indicators to study the impact of the current crisis on different population cohort. Publish the data trend. Advise on programme designs according to trends. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
| Sector Advocacy Efforts | Strenghten advocacy around resource mobilisation including strengthening funding gap analysis, visibility of partners projects and gaps in assistance etc. Develop key messages for the Sector and contribute with inputs and support to other partners and inter-sector efforts for resource mobilisation for the LCRP. | X |  | X |  | Food Security & Agriculture Sector Coordinators (WFP/FAO) | IAWG, Sectors, LCRP partners, donors |  | Ongoing
|  | Update advovacy note on removal of subsidies and impact on food security and agriculture |  | X |  |  | Food Security & Agriculture Sector Coordinators (WFP/FAO) | WFP RAM unit, gFSC |  | Ongoing
|  | Work with protection, nutrition and child protection working groups/sectors to highlight issues, strengthen partners capacities to monitor, address and mitigate risks through advocacy, awareness and guidance | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
|  | Advocate for adjustments to transfer values for cash and voucher assistance, to account for inflationary trends and currency depreciation | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | LCRP Sectors, Ministry of Social Affairs |  | Ongoing
| Inter-Sector Coordination | Livelihoods: coordinate and support new and existing thematic working groups and joint approaches to strengthen linkages between the two sectors' intervention (livelihoods, agricultural value chains, cooperatives/associations etc) | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) | Ministr yof Agriculture, Livelihood Sector and relevant partners |  | Ongoing
|  | Basic Assistance: coordinate and strenghten linkages and joint approaches with the sector including development of guidelines, monitoaring frameworks, deduplication and complementariety | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
|  | Nutrition/Health/Education: coordinate and strengthen linkages, joint approaches and referrals to improve nutritional outcomes for vulnerable households | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
|  | Social Stability/Protection: coordinate and stengthen linkages with sectors and working groups (e.g. child protection, GBV) to identify gaps, assess risk, establish mitigation measures, develop guidance | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
| Reporting | Keep ActivityInfo reporting updated | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
|  | Keep the Inter-Sector service mapping updated | X | X | X | X
|  | Produce quarterly reporting dashboards | X | X | X | X
|  | Update the interactive dashboards | X | X | X | X
IS Joint Priority 1 | Sector Situation Analysis | Contribute to analysis of food security and agriculture sector trends, gaps etc and with inputs into vulnerability assessments, definition of targeting criteria etc | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
|  | Strengthen monitoring frameworks, assessments analysis and reports (including results from post-distribution monitoring, and other outcome and process monitoring) to inform programmes and joint activities/approaches | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
IS Joint Priority 2 | Cash and Voucher Assistance | Coordinating with the Basic Needs Sector with regard to CBT modalities. Coordinating best practice and guidelines, including CBT in agriculture. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
IS Joint Priority 3 | Agricultural Livelihoods | Keep on supporting and facilitating existing related coordination fora and tools (e.g.: Active Dashboard on Coops and Livelihood, bi-monthly coordination meeting of Agri-Coops/MSNE). Exploring new relevant thematic topics jointly with the Livelihood Sector. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
Mainstreaming area | Protection/PSEA | Ensure gender-sensitive programming by strengthening the targeting, delivery and monitoring of interventions that take into consideration the differential needs of women, men, girls and boys. Strengthen the safe identification and referral of persons with specific needs and individuals at risk. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
| Conflict Sensitivity | Strengthen conflict sensitivity and do no harm approaches in partners’ capacities and operations through guidance, training, monitoring and linkages with other sectors. Quarterly updates on the Tensions Landscape at FSAS Working Groups. Thematic discussions with Conflict Sensitivity focal point. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO), CS Mainstreaming FP |  |  | Ongoing
|  | Together with the Social Stability sector, the Food Security and Agriculture sector will finalise conflict sensitivity guidelines with a view to expand them to include food assistance and agricultural livelihoods interventions. |  |  | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
| Environment | Coordinate with ETF to ensure that activities are in line with environmental safeguards, namely with regards to the adoption of Sustainable Land Management practices. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
|  | ActivityInfo reporting on agri-related activities | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
| COVID-19 | Ensure the provision of services both in-person and through remote modalities, while continuously review and adapt tools and guidance for the provision of safe and accessible programming in the context of COVID-19. | X | X | X | X | Food Security & Agriculture Sector Coordinators (WFP/FAO) |  |  | Ongoing
| Gender and SGBV | Gender in Humanitarian action training is conducted in 2022 at national and regional level with the support of Inter-Agency Gender Specialist. |  | X | X | X | Gender/SGBV FP, Coordinator and Gender Specialist |  |  | Ongoing
|  | Guidelines/recommendations drafted with support from Inter-Agency Gender Specialist, including the promotion of SGBV risks analysis and SGBV risk mitigation measures. |  | X | X | X | Gender/SGBV FP, Coordinator and Gender Specialist |  |  | Ongoing
|  | Nomination of gender and SGBV Focal point of the sector |  | X |  |  | Gender/SGBV FP and Coordinator |  |  | Ongoing
|  | Analyse disaggregated sector results on a quarterly basis and produce programmatic recommendations to address gender inequalities. | X | X | X | X | Coordinator and Gender Specialist |  |  | Ongoing
|  | Keeping the mapping of women's Agri-Coops/MSME updated regulraly. | X | X | X | X | Coordinator and Gender Specialist |  |  | Ongoing

## Logframe Activities
2022 LCRP Food Security and Agriculture Sector Workplan - Logframe Activities
2022 Timeline
Sector Output | Key Activities | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Additional Comments | Status
Outcome 1: Improve food availability through in kind food assistance and sustainable food/agriculture value chain
OUTPUT 1.1 Vulnerable individuals have access to nutritionally balanced in-kind food assistance | Activity 1: Provision of in-kind food assistance (food parcels, hot meals, ready to eat foods) to address vulnerable people's immediate food needs. | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | CARITAS, URDA, Farah Social Foundation, IR Lebanon, CCP Japan, CARE, SD Aid, Anera, Tabitha/Dorcas, BASSMA, Common Effort, FoH, AVSI, Nusaned, ACF Spain | Special attention will be paid to ensure households with Pregnant and Lactating Women (PLW) and/or with children <5 years of age are reached through adequate/nutrition-sensitive in-kind support. Also special attention will be paid to ensuring that in-kind assistance is supplemented by fresh produce, including by strengthening linkages between partners and local producers. This activity is closely linked to Outcome 3 / Output 3.1
OUPUT 1.2 Lebanese small-scale farmers have strengthened capacities in agricultural value chains, in reduction of food waste/losses, sustainable and climate-smart practices and in plant pest and transboundary animal diseases measures | Activity 1: Provision of inputs, training and/or technical support in agricultural and livestock practices targeting small-scale farmers, including strengthening linkages to markets. | X | X | X | X | Food Security and Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | ACTED, ANERA, Arcenciel, ARCS, CONCERN, COOPI, Fair Trade Lebanon, FAO, GVC, IOCC Lebanon, LOST, Nusaned, OXFAM, PCPM, PU-AMI, RI, SBT, SCI, SHEILD, Solidarités international, WVI | Under this activity, support will be tailored around the following areas a) farming practices/ production b) natural resource conservation c) climate-smart agriculture practices d) food waste and losses and valorization of organic waste e) improving storage conditions f) post-harvest management (labelling, packaging etc.)
| Activity 2: Supporting emergency interventions to control the spread of transboundary diseases, including through monitoring and early warning systems for plant pests and animal diseases and vaccination campaigns | X | X | X | X | Food Security and Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | FAO, Ministry of Agriculture | This support aims at providing vaccines against animal diseases for livestock and through the concerned Department of the ministry of Agriculture.
Outcome 2: Improve food access through cash-based food assistance and support to sustainable agricultural livelihoods
OUTPUT 2.1 Vulnerable populations have access to cash-based food assistance and have improved access to food | Activity 1: Provision of cash-based food assistance (cash and/or vouchers) to address vulnerable people's immediate food needs | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | WFP, Ministry of Social Affairs, MERATH, MCC, CARITAS, ANERA, CARE, Nusaned, CONCERN, ADRA, UNRWA, Women Charity League | This activity includes the provision of cash-based food assistance to all population cohorts, including vulnerable Lebanese registered in the National Poverty Targeting Programme, across different delivery mechanisms direct cash, e-cards, vouchers etc. Special attention will be paid to ensure households with Pregnant and Lactating Women (PLW) and/or with children <5 years of age are reached through cash-based food assistance and activities implemented under Outcome 3, Output 3.1
OUTPUT 2.2 Farmers associations, cooperatives and agricultural MSMEs have increased capacities in production, transformation, governance along the value chain and have improved agricultural livelihoods | Activity 1: Provision of farmers associations and/or cooperatives/ agricultural MSMEs with financial support (i.e. grants/credit schemes), inputs, technical assistance and/or capacity building | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | ACTED, Arcenciel, ARCS, AVSI, CONCERN, COOPI, Fair Trade Lebanon, FAO, Farah Social Foundation, GVC, Leb Relief, LOST, Nusaned, OXFAM, PCPM, PU-AMI, RI,Safadi Foundation, SBT, SCI, SHEILD, tsa, WVI | This activity aims to improve capacities on Good Agricultural Practices (management of soil resources, pest management and efficient use of water resources), on governance/laws and regulations of cooperatives and strengthen linkages to markets
OUTPUT 2.3 Lebanese small-scale farmers have access to emergency, recovery and/or long-term support (in kind/inputs, financial, technical) that promote agricultural investment | Activity 1: Provision of cash and/or voucher transfers to promote agricultural investments | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | FAO, Ministry of Agriculture | This activity corresponds to support farmers through the provision of agricultural inputs (seeds, fertilizers, equipment etc..) to allow them maintain their production activities during 2022
| Activity 2: Provision of technical and/or financial support and training to strengthen agricultural investments, access credit/loan investment schemes, and on profitable farming business opportunities | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | ACF Spain, ACTED, Arcenciel, AVSI, B&Z,COOPI, Fair Trade Lebanon, FAO, Farah Social Foundation, GVC, LOST, Nusaned, PU-AMI, Safadi Foundation, SBT, SHEILD, UNDP | Provision of financial (grants) and technical support for agriculture private sector investment (e.g. to access and utilize unproductive land through land reclamation, terracing, irrigation/water management)
OUTPUT 2.4 Youth aged 15 to 25 years have access to improved agricultural technical education and vocational training | Activity 1: Provision of agricultural vocational skills training and/or basic literacy and numeracy (formal and/or informal education) | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | Arcenciel, Caritas Lebanon, COOPI, DRC, Farah Social Foundation, GVC, Leb Relief, Nusaned, Rahma Association, RI, SBT, SHEILD, SIF, UNICEF, WVI | Focus on youths aged 15 to 25 years specifically under short vocational trainings.
OUTPUT 2.5 Vulnerable individuals have improved opportunities to access temporary, seasonal and casual labour in agriculture and related sectors, in exchange for cash assistance to increase their access to food and to agricultural infrastructure and assets | Activity 1: Provision of temporary, casual and/or seasonal work in rehabilitation/development of assets and infrastructure in exchange for cash-based food assistance | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | ACTED, AFDC, Arcenciel, AUB, AVSI, CONCERN, COOPI, FAO, LOST, LRI, PCPM, PU-AMI, RI, RMF SBT, SHEILD, SIF, UNICEF, WFP, WVI | This activity includes Food for Assets programmes and other cash-for-work initiatives.
OUTPUT 2.6 Vulnerable individuals have strengthened technical and operational capacities to access temporary, seasonal and casual labour, in exchange for cash-based assistance that increases their access to food | Activity 1: Provision of training/skills development opportunities to increase access to income-generating opportunities, in exchange for cash-based food assistance | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | ACS, ACTED, Arcenciel, AUB, COOPI, GVC, ICU, IOCC Lebanon, LRO, PCPM, PU-AMI, RI, RMF, Safadi Foundation, SBT, shareQ, SHEILD, SIF, WFP | This activity includes Food for Training programmes
Outcome 3: Improve food utilization through food safety and nutrition practices (promotion of consumption of diversified/quality food and IYCF practices)
OUTPUT 3.1 Individuals and households more vulnerable to food insecurity (women-headed households, households with pregnant and lactating women and children under five, households with individuals over 65 years old) adopt optimal nutrition practices. | Activity 1: Promotion of optimal nutrition related behaviours and practices among Pregnant and Lactating Women and caregivers of children under 5 years, including promotion of adequate IYCF practices, nutrition awareness sessions, training on food preservation/transformation technologies, enrolment in malnutrition programmes | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | ACF, BASSMA, WFP, Ministry of Social Affairs, Ministry of Public Health, UNICEF, WHO, CARITAS, URDA, Farah Social Foundation, IR Lebanon, CARE, Anera, Tabitha/Dorcas, FoH, AVSI, Nusaned | This activity includes close linkages with the work of the health and education sector and nutrition working group, including referrals form these sectors to ensure the FSS can, to the extent possible, match requests for in-kind/cash support to vulnerable groups with partners providing food assistance
OUTPUT 3.2 Individuals have improved capacity on food safety and quality to improve their practices. | Activity 1: Provision of training on Pest Management and Good Agriculture Practices and Standards and on food safety and quality measures/practices with a focus on women and girl's employment | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | B&Z, Borderless, CONCERN, COOPI, FAO, GVC, MAP-UK, Nusaned, Rahma Center for Community Services, Salam LADC, SBT,SHEILD | This activity aims at providing trainings and technical support to mainly small-scale farmers to adopt Good Agricultural Practices and Integrate pest management within their farming practices. Thess activities could take place at any time of the year, depending on specific seasonal requirements.
Outcome 4: Promote and stabilize food security through support/ capacity building and strengthening of national public institutions and their decentralised services
OUTPUT 4.1 National and decentralised institutions working in food security, agriculture and social protection have strengthened capacities to improve service delivery for vulnerable populations | Activity 1: Provision of strategic, operational and/or technical support, as well as of equipments and training to strengthen service delivery capacity of institutional partners | X | X | X | X | Food Security & Agriculture Sector Lead (MoA) & Co-leads (WFP & FAO) | Minstry of Agriculture, Ministry of Social Affairs, WFP, FAO, Municipalities, ACF, Social Welfare Officers, CARE, CARITAS, BASSMA, Tabitha/Dorcas, MCC, ADRA, MERATH, Green Plan, General Directorate of Cooperatives | Provision of strategic, technical and/or operational support to national and decentralised institutions to strengthen their food security, agriculture and social protection programmes and services delivery