| **Recommendation** | **Relevant Indicator(s)****(see Guidelines)** | **Next step(s)**  | **Timeline** | **Responsible contacts(s)** | **Resources Needed** |
| --- | --- | --- | --- | --- | --- |
| Improve the coordination of service providers on GBV | * coordination network is in place and functioning
* Satisfaction of survivors from service provision
 | * Conference for all relevant and targeted NGOs/ services providers
* Enterprise system (IT) to coordinate the referral between agencies
* Standardizing the standards and procedures in dealing with GBV cases
 | 1 year | Focal points of different NGOs | HR, resources, IT company, NGOs focal points  |
| Availability/ and accessibility of GBV and protection 24/7 | * # of health facilities with available and accessible 24/7 GBV services
* # of staff allocated during the day
* Ratio of females/ males within the services
 |  | On going  | Health related project managers  | HR |
| Available women doctors in clinics  | * # of female staff
 | * Increase accessibilities to work in camps to female doctors
* Advocacy
 | 3months  | Project coordinators | HR |
| Raising staff awareness on GBV and referral pathways  | * Staff knowledge about SOPs for multi sectoral sectors for GBV response
 | * Get approvals for trainings
* Training of staff
 | Feb-April 2017 | Resources, responsible agencies (PUI) | Budget, trainers  |
| Build the capacity of the health providers on the referral mechanisms for GBV survivorsBuild the capacity of the health providers on case management (CMR) for GBV survivors | * Satisfaction survey results pre/post
* Pre/post tests for the staff
 | * Coordination with agencies to conduct GBV basic training and on SOPs
* Create the pre/post survey
* Conduct the capacity building
 | 1 year | PMsHR | Budget Trainers  |
| Support community-based health promotion activities.( for young married women who do not readily access health services,  | * IEC materials with

health messages tackling sensitive issues such as SGBV and STIs. | Follow up of health care providers working at facility level | 1year | Focal points at different NGO’s |  Trained staff and financial support  |