| **Recommendation** | **Relevant Indicator(s)**  **(see Guidelines)** | **Next step(s)** | **Timeline** | **Responsible contacts(s)** | **Resources Needed** |
| --- | --- | --- | --- | --- | --- |
| Improve the coordination of service providers on GBV | * coordination network is in place and functioning * Satisfaction of survivors from service provision | * Conference for all relevant and targeted NGOs/ services providers * Enterprise system (IT) to coordinate the referral between agencies * Standardizing the standards and procedures in dealing with GBV cases | 1 year | Focal points of different NGOs | HR, resources, IT company, NGOs focal points |
| Availability/ and accessibility of GBV and protection 24/7 | * # of health facilities with available and accessible 24/7 GBV services * # of staff allocated during the day * Ratio of females/ males within the services |  | On going | Health related project managers | HR |
| Available women doctors in clinics | * # of female staff | * Increase accessibilities to work in camps to female doctors * Advocacy | 3months | Project coordinators | HR |
| Raising staff awareness on GBV and referral pathways | * Staff knowledge about SOPs for multi sectoral sectors for GBV response | * Get approvals for trainings * Training of staff | Feb-April 2017 | Resources, responsible agencies (PUI) | Budget, trainers |
| Build the capacity of the health providers on the referral mechanisms for GBV survivors  Build the capacity of the health providers on case management (CMR) for GBV survivors | * Satisfaction survey results pre/post * Pre/post tests for the staff | * Coordination with agencies to conduct GBV basic training and on SOPs * Create the pre/post survey * Conduct the capacity building | 1 year | PMs  HR | Budget  Trainers |
| Support community-based health promotion activities.(  for young married women who do not readily access health services, | * IEC materials with   health messages tackling sensitive issues such as SGBV and STIs. | Follow up of health care providers working at facility level | 1year | Focal points at different NGO’s | Trained staff and financial support |