## AWP 2022 - Joint IS PRTCPGBV
2022 Protection Sector Workplan - Sector Coordination / Inter-Sector priorities
2022 Timeline
Link to logframe & cross-sector/mainstreaming priorities | Theme | Key Priorities | Main actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main partners (optional) | Additional Comments | Status | Status | On/Off track
Please specify the link: - with your sector output and/or activity - or with the IS priority |  | List the key priorities identified | List the main actions that will be taken to ensure that each priority is adressed | Specify the timeline of implementation for each action |  |  |  | Specify who, within the coordination team (coordinator, IMO, core group…) is responsible for implementing this action | List the main partners involved in each activity |  | On track: green Pending/on-going: orange Off track: red | Description of status. Monitoring of implementation to be done at the end of each quarter (May 2021)
Output 1.1. Women, men, girls and boys in all their diversity have access to information on legal topics and know how to access their rights | Rights Awareness | Ensure hollistic prevention and response approach to child marriage | Review IA Guidance on child marriage - with CP/GBV/PRT sector incl.legal
|  | National birth registration action plan | Review zero-draft of national birth registration action plan and participate in validation workshop | X | X |  |  | PWG / MOSA | CP and SGBV core groups/LAWG members
Output 2.3: Known, accessible and available complaint and feedback, protection against sexual exploitation and abuse (PSEA) and child safeguarding mechanisms are in place. | Accountability for affected populations: Complaints & Feedback | Ensuring that CFM are inclusive and child-friendly | Regular presentation by NGOs who have CFM to show disagregated data , incl. on identified gaps and who is reaching reaching out (children? PwDIS ?) | X | X | X | X | PRT Mainstreaming Specialist
|  |  | Ensuring that material related to child friendly CFM is consolidated and accessible to all. | X | X |  |  | CP Coordinator with CG
|  | Increasing access to PSEA ressources and opportunities for training | Mainstreaming information related to PSEA in WG/TF regulalry. Contributing on information collection on training needs. | X | X | X | X | Cp/GBV/PRT coordinators
|  | Support protection partners meeting PSEA standards | Conduct a survey among members on exisitance of Code of Conducts and complaint mechanisms |  |  | X |  | PSEA Coordinator
|  | Improve capacities of helpline responders to respond to high risk cases on severe MHPSS needs | Sharing lessons learned from WFP on training for phone operators on severe MHPSS needs. To ensure that we better know how to respond to immediate needs through CFM + how to make sure we are effective in referrals |  | X |  |  | GBV Coordinator
Output 3.1: Protection, CP and GBV services, including mental health and psychosocial services, are available, accessible, safe and informed by women, men, girls and boys in all their diversity. | Protection Case Management | Provide partners with clearer guidance on protection case management inc. case coordination between CP, GBV, PRT and prioritisation of cases | Review and compile existing guidance and tools on case management of children survivors of GBV with CP and GBV sectors, including proper roll-out of Caring for Child Survivors with field workers. |  | X | X |  | Case management TF
|  |  | Provide guidance on how to respond to the needs of survivors of trafficking through case management for PRT, CP, GBV inc. safe identification and referrals and technical support on the case management of survivors of trafficking. |  | X | X |  | IOM and KAFA
| MHPSS | Improve early identification and referral of MHPSS cases between PRT and Health | Support MHPSS TF to review needs of trainings on SIR : contibute to the development of the survey on staff needs (# of staff and what information is needed by frontliners) . Support the roll out of the trainings as required |  | X |  |  | CP/GBV/PRT Coordinators | 3 CG
|  |  | Ensure MHPSS service mapping is accessible and udpated - in coordination with MHPSS TF | X |  |  |  | PRT sector assistant - FP for IS Referrals
|  | Staff & Self Care ( PFA Training ) | Create TF (Education/CP/GBV/PRT sectors) on Staff Care. The TF will be responsible for creating a commun repository for material related to staff care + ensuring thayt the 4 sectors conduct a survey related to staff care (developped under CP sector) + organizing a joint discussion on the outomes of the survey, challenges, needs, opprtunities and good practices + developing a joint action plan for advocacy for mainstreaming Staff care | X |  |  |  | CP/GBV/PRT/EDUC Coordinator | to be identified
Coordination |  | Reporting | Keep ActivityInfo reporting updated | X | X | X | X | CP/GBV/PRT Coordinators
|  |  | Keep the Inter-Sector service mapping updated | X | X | X | X
|  |  | Produce quarterly reporting dashboards | X | X | X | X
|  |  | Update the interactive dashboards | X | X | X | X
Mainstreaming |  | Gender | Gender in Humanitarian action training is conducted in 2022 at national and regional level |  | X | X | X | Coordinator and Gender Specialist
|  |  | Gender analysis two pager is drafted with support from Interagency Gender Specialist |  | X |  |  | Gender/SGBV FP, Coordinator and Gender Specialist
|  |  | All FSA assessments include gender specific questions and gender analysis | X | X | X | X | Gender/SGBV FP and Coordinator
|  |  | Nomination of gender and SGBV Focal point of the sector | X | X | X | X | Gender/SGBV FP and Coordinator
|  |  | Feedback mechanisms involve at least 50% of women and girls | X | X | X | X | Gender/SGBV FP and Coordinator
|  |  | Analyse disaggregated sector results on a quarterly basis and adapt activities to address gender inequalities | X | X | X | X | Coordinator and Gender Specialist
|  | Conflict Sensitivity | Mainstreaming- Conflict Sensitivity: Quarterly updates on the Tensions Landscape at FSS Working Groups Thematic discussions with Conflict Sensitivity FocalPoint Training partners on conflict sensitivity | X | X | X | X | CS Mainstreaming FP

## PRT AWP 2022 DRAFT
2022 Protection Sector Workplan - Sector Coordination / Inter-Sector priorities
2022 Timeline
Link to logframe & cross-sector/mainstreaming priorities | Theme | Key Priorities | Main actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main partners (optional) | Additional Comments | Status | Status | On/Off track
Please specify the link: - with your sector output and/or activity - or with the IS priority |  | List the key priorities identified | List the main actions that will be taken to ensure that each priority is adressed | Specify the timeline of implementation for each action |  |  |  | Specify who, within the coordination team (coordinator, IMO, core group…) is responsible for implementing this action | List the main partners involved in each activity |  | On track: green Pending/on-going: orange Off track: red | Description of status. Monitoring of implementation to be done at the end of each quarter (May 2021)
Output 1.1. Women, men, girls and boys in all their diversity have access to information on legal topics and know how to access their rights | Rights Awareness | Hamonise messaging on civil documentation | To review and standardise key messages on birth and marriage registration |  |  |  |  | UNHCR, NRC | Education, CP, GBV, PRT | Activity is part of proposed national birth registration action plan 2022. Compilation of partner materials has taken place in 2021. Is the plan to develop standard messages or just provide recommendations?
|  | Ensure hollistic prevention and response approach to child marriage | Review IA Guidance on child marriage - with CP/GBV/PRT sector incl.legal |  |  | X |  | PRT Coordinator and GBV Coordinator | LAWG, CP, GBV, PRT sectors (to be further defined)
Output 1.2: Women, men, girls and boys in all their diversity have access to legal counselling, assistance and representation | Legal service provision | Cross-sector prevention & response to eviction Joint-planning Shelter, Protection, SOST. | Finalise cross-sector individual eviction guidance note | X |  |  |  | PWG | DRC, IRC, Caritas, NRC, Intersos, PUAMI | Review needed by: National PRT, LAWG and Shelter, BA, FSA, LH, GBV sector coordinators; PRT Field Officers, Shelter Sector Field Officers, HLP TTC & LAWG members, CS & gender specialists
|  |  | Inter-sector eviction TF at national level: to share lessons learnt, best practices, increase visibility, advocacy and mobilisation of funds, information flow to expediate preparedness, support operationalisation of individual eviction note | X | X | X | X | Protection Mainstreaming Co
|  |  | Share best practices and lessons learned on provision of legal aid in particular on legal mediation to prevent eviction - in coordination with IS Eviction TF |  | X | X |  | LAWG | In close coordination with IS Eviction TF once created | DRC shared a report on lessons learnt: eviction workshop in Bekka / Eviction TF in North.
Output 1.3 Protection and legal frameworks are strengthened and implemented accurately and evenly to better respond to the protection needs of women, men, girls and boys in all their diversity. | System protective of rights | Strengthening evidence-based advocacy in line with strategic priorities | Share information on topics pertinent to advocacy priorities and share findings from monitoring of practices at GSO, PSD, Border, and in relation to other authorities (mokhtar, sharia'a courts) and schools and health facilities | X | X | X | X | LAWG | All LAWG members Education, Health Sector Coordinators | Frequency: LAWG meets every 2 months. Including sector strategies on specific advocacy areas, results from restrictive measures dashboard, protection monitoring, legal monitoring of practices. Improve referral pathways.
|  |  | Discussion on legal residency addressing commitments (stock-taking GOL/donor-side), challenges and presenting concrete deliverables |  | X |  |  | LAWG
|  | National birth registration action plan | Review zero-draft of national birth registration action plan and participate in validation workshop | X | X |  |  | PWG / MOSA | LAWG members
|  | National older person action plan | To review the national older persons action plan and agree on sector position |  |  | X |  | Protection Coordinator, MOSA
|  | Advocacy strategy | To review and endorse advocacy key priorities |  | X |  |  | PRT Coordo |  | invite HRO CSO
Output 2.1: Women, men, boys and girls in all their diversity have the information and resources to act upon informed decisions and participate in inclusive and accessible community spacesx | SOST & Protection Joint planning with SOST + SGBV TF | Contribute to social stability outcomes | Support discussions at field level on training plans to local authorities. To map and share PRT and SOST capacity building plans with local authorities (topic, location) to ensure complementarity of topics (PRT: gender, SGBV, human rights and anti-trafficking) and avoid overlap. |  | X | X | X | to ask : PRT field coordination - provide support as needed | IOM, SGBV TF Coordinator, Gender specialist | Activity is organised by SOST with PRT sector support for delivery of sessions. To request SOST training plan for 2022 and agree on priority areas to train. Needs discussion with SOST. Consider launch of EOI. To discuss speciifc training needs (capacity asssessment).
| Strengthened partnerships with CBO/NNGO | Improve knowledge of and engagement of NNGO in coordination spaces | Explore ways to enhance relationship with local NGOs incl. in discussion with existing local NNGO forums | X | X |  |  | Protection Assistant | PASC, LHDF Forum, LUPD Forum
|  |  | Translate key protection sector guidance to Arabic | X | X |  |  | Protection Assistant. | IA Assistant. | To review key documents and arrange translation.
|  |  | Provide simutaneous translation in PWG for 2022 | X | X | X | X | Protection Mainstreaming Co | IA Assistant.
|  | Keep strengthening partnerships with NNGO working on disability and older persons issues | Conduct follow-up focused discussion with specialised N/INGO to review protection concerns,challenges and needs incl. related to outreach modalities for older persons and persons with disability (channel into advocacy messages for specialised services for PWSN by PCM TF + in focus for older persons) |  | X |  |  | Protection Coordinator | WRF as coordinator of DIS WG and Helpage | To include local organisations working on issues related to disability and older persons rights through DISWG and jointly plan workshop - some areas; issue donor advocacy points, review of assessments,tailored outreach modalities, share lessons learnt etc. Advocacy messages for specialised services is also a priority for PCM TF & Mainstreaming.
CP/GBV sub-sector
| CBP | Finalise and roll out CBP guidance | Conduct final review of CBI guidance and endorsment | X |  |  |  | Protection Assistant. CBI TF |  | CBI document is preliminary drafted. Review by: CBI Task Force, sector coordinators, field PO, Gender, PSEA, GBV and CP coordinators, PCG members.
|  |  | Introduce the document with all CBI actors and relevant actors in other sectors (through workshop or other modality) |  | X |  |  | CBI TF |  | Cross sectoral discussion to take place in order to identify priority sectors and agree on way forward.
Output 2.3: Known, accessible and available complaint and feedback, protection against sexual exploitation and abuse (PSEA) and child safeguarding mechanisms are in place. | Accountability for affected populations: Complaints & Feedback Joint planning with CP/PRT/GBV/PSEA network | Ensuring that CFM are inclusive and child-friendly | Regular presentation by NGOs who have CFM to show disagregated data , incl. on identified gaps and who is reaching reaching out (children? PwDIS ?) | X | X | X | X | CP coordinator with CG
|  |  | Ensuring that material related to child friendly CFM is consolidated and accessible to all. | X | X |  |  | CP Coordinator with CG
|  | Increasing access to PSEA ressources and opportunities for training | Mainstreaming information related to PSEA in WG/TF regulalry. Contributing on information collection on training needs. | X | X | X | X | Cp/GBV/PRT coordinators |  | CPWG is working on an inter-agency SOP on hotlines.
|  | Support protection partners meeting PSEA standards | Conduct a survey among members on exisitance of Code of Conducts and complaint mechanisms |  |  | X |  | PSEA Coordinator
|  | Improve capacities of helpline responders to respond to high risk cases on severe MHPSS needs | Sharing lessons learned from WFP on training for phone operators on severe MHPSS needs. To ensure that we better know how to respond to immediate needs through CFM + how to make sure we are effective in referrals |  | X |  |  | GBV Coordinator | Amel | How to move the IACFM guidelines and checklist forward?
Output 3.1: Protection, CP and GBV services, including mental health and psychosocial services, are available, accessible, safe and informed by women, men, girls and boys in all their diversity. | Protection Case Management Joint planning with CP/PRT/GBV | Provide partners with clearer guidance on protection case management inc. case coordination between CP, GBV, PRT and prioritisation of cases | Review and compile existing guidance and tools on case management of children survivors of GBV with CP and GBV sectors, including proper roll-out of Caring for Child Survivors with field workers. |  | X | X |  | Case management TF
|  |  | Provide guidance on how to respond to the needs of survivors of trafficking through case management for PRT, CP, GBV inc. safe identification and referrals and technical support on the case management of survivors of trafficking. |  | X | X |  | IOM and KAFA
| Support to PwSN, esp. older persons and persosn with DIS | Enhancing specific support to PwDIS and older persons , and fostering inclusion in mainstream services | Develop an in Focus documents on PwDIS and older persons |  | X |  |  | PRT ccordinator | CG members, Forum of PwDIS | Follow-up discussion fo 2021 PWG session on same theme to take place, with relevant local NGOs and other entities.
| MHPSS Joint-planning with Health, CP, GBV, National MHPSS TF | Improve early identification and referral of MHPSS cases between PRT and Health | Support MHPSS TF to review needs of trainings on SIR : contibute to the development of the survey on staff needs (# of staff and what information is needed by frontliners) . Support the roll out of the trainings as required |  | X |  |  | CP/GBV/PRT Coordinators | 3 CG
|  |  | Ensure MHPSS service mapping is accessible and udpated - in coordination with MHPSS TF | X |  |  |  | PRT sector assistant - FP for IS Referrals
|  | Staff & Self Care ( PFA Training ) | Create TF (Education/CP/GBV/PRT sectors) on Staff Care. The TF will be responsible for creating a commun repository for material related to staff care + ensuring thayt the 4 sectors conduct a survey related to staff care (developped under CP sector) + organizing a joint discussion on the outomes of the survey, challenges, needs, opprtunities and good practices + developing a joint action plan for advocacy for mainstreaming Staff care | X |  |  |  | CP/GBV/PRT/EDUC Coordinator | to be identified
| Cash Joint-planning with BA, LH, FSA | Provide clearer guidance and coordination on cash practices | Conduct a 'light-touch' review of ECA guidance | X |  |  |  | PM Lead | Extended ECA TF members + Field ECA TF
|  |  | Draft sector protection cash guidance and hold validation workshop with ECA TF members | X |  |  |  | PM Lead | Extended ECA TF members + Field ECA TF
|  | Address systemic referral challenges for sustainable interventions (BA and FSA) | Explore referral pathway for MPCA linked to non-UN agencies (drawing on good practices between NGO integrated protection and basic assistance cash projects) |  |  |  |  | PM Lead
|  |  | Review cash-for-rent guidance drafted by Shelter sector (ensure complementarity with ECA) | X |  |  |  | PM Lead | Extended ECA TF members + Field ECA TF
|  | Mainstream PRT lens in communication/appeal mechanism on MPCA/Food assistance | Review cash communication products |  |  | X |  | PM Lead |  | Annually sent ahead of inclusion/exlcusion message
|  |  | Engage in the review of the GRM process |  |  | X |  | Protection Coordinator | PM Lead | To check timeline of review with BA.
|  | Improve cash MEAL practices | Review cash core indicators in 2022 |  |  | X |  | PM Lead | Expanded ECA TF | Drafted. Need to update with partners in 2022.
|  |  | Quarterly reporting on core cash indicators as part of AI quarterly reporting (Field and national) | X | X | X | X | National & Field POs | IM Officer | Ongoing
|  |  | Mainstream PRT AGDD lens in BA cash modality through attendance of M&E TF and review of monitoring tools | X | X | X | X | GBV Coordinator, Gender Specialist |  | Ongoing.
Assumptions, Risks, Mitigation Measures | Mitigation measures Joint-planning with GBV, CP | Advocate with donors for sufficient funding & flexible funding arrangements | Conduct a joint GBV, CP, PRT donor briefing to introduce sector strategy, prioritisation, funding gaps and other key sector advocacy priorities for 2022 - twice a year |  | X |  | X | PRT, CP, SGBV Coordinator |  | To use results and recommendations of socio-economic impact survey on protection programmes. Joint action with CP, GBV.
|  | Ensure buisness continuity | Engage partners in updating of the LCRP Business Continuity Plan |  | X |  |  | PRT, CP, SGBV Coordinator | CP, GBV, PRT CG members + field. | Inter-sector led process.
Mainstreaming | Protection Mainstreaming | Improve referrals across sectors | Quarterly review of progress on sector referrals at field and national level and make recommendations on gaps / addressing bottle necks | X | X | X | X | Protection, CP, GBV Coordinators | PRT, CP, GBV Field Coordinators | Ongoing activity conducted on quarterly basis.
|  |  | Conduct review of IA referral tools and update accordingly |  | X |  |  | Protection Mainstreaming Co. Protection Assistant. | IM Officer, Inter-Sector | To focus on the needs and challenges of sector coordinators in following up bottlenecks in referrals and in using/actioning the referral reporting
|  |  | Quarterly orientation sessions provided on introduction to inter-agency referral tools | X | X | X | X | Protection Mainstreaming Co. | IM officer, Protection Assistant. | To launch quarterly trainings on set date each 3 months.
|  |  | SIR training offered specific for NNGO |  | X |  |  | Protection Mainstreaming Co |  | Previously arranged with PASC network + to expand.
|  | Specific technical support to other sectors (priority in 2022 to shelter and basic assistance) | Review and provide technical support on key priorities in Shelter & Basic Assistance sector protection risk analysis | X | X |  |  | Protection Mainstreaming Co |  | This in itself opens up many different tasks depending on selected priorities.
|  |  | Support IS discussion on good practices and recommendations and dissemination of existing tools disability and age inclusion (priority sectors to be identified based on relevance, interest and capacities) |  | X | X |  | Protection Mainstreaming Co
|  | Protection analysis | Quarterly protection situation update compiled and reviewed by CG members and shared in PWG | X | X | X | X | Protection Coordinator | PCG Members | Ongoing monthly activity.
|  |  | Quarterly update of protection analysis through latest reports / analysis | X | X | X | X | Protection Mainstreaming Co, CP, GBV Coordinators
|  |  | Review existing analysis plans and questions in key assessment tools to capture protection risks |  | X |  |  | Protection Mainstreaming Co
|  |  | In focus: Older persons at risk + PwDIS |  | X |  |  | Protection Mainstreaming Co | IA Gender specialist, CBP colleagues, PCM colleagues. Selected NNGO working on PWD / Older persons issues. | Link this activity to strengthening partnerships with NNGO in outcome 2 + advocacy messages needed on specialised services for PCM + build on 2021 PWG and DISWG discussion and expand to other sectors on best practice for inclusion and use of IASC Guidelines
PWG Functioning & 2022 Planning process preparation | Planning | Budget development | Develop accurate average unit cost per protection intervention |  |  | X |  | Protection coordinator |  | Start in August in time for planning. Based on gaps noted in planning process for 2022
|  | Gap Analysis | Review and generate needs based target per intervention per govenorate to use as baseline for gap analysis |  |  | X |  | Protection coordinator |  | Based on gaps noted in planning process for 2022. Governorate level project reporting started by partners to allow for more specific gap analysis.
|  | Reporting | Update reporting matrix with indicators; detailing description, dissagregation level etc. | X |  |  |  | IM for protection | Protection Co | Annual activity
|  |  | Training on AI for partners on new indicator | X |  |  |  | IM for protection | Protection Co. | Annual activity
|  |  | Produce quarterly dashboard and review progress quarterly in regional and national PWG | X | X | X | X | IM for protection & protection coordinator. |  | Ongoing. | Complete
|  | Other | Maintain protection sector folder to ensure access to resources | X | X | X | X | Protection Assistant. |  | Monthly. | Complete
|  |  | Monthly attendance of key sector WGs by CG members | X | X | X | X | Protection Coordinator | CG members, Protection Mainstreaming Co, Protection assistant. | BA & FSA (IRC), LH, Shelter, Health, CP & GBV (MOSA)
Joint priorities CP/GBV/PRT
Mainstreaming |  | Gender | Gender in Humanitarian action training is conducted in 2022 at national and regional level |  | X | X | X | Coordinator and Gender Specialist
|  |  | Gender analysis two pager is drafted with support from Interagency Gender Specialist |  | X |  |  | Gender/SGBV FP, Coordinator and Gender Specialist
|  |  | All Protection assessments include gender specific questions and gender analysis | X | X | X | X | Gender/SGBV FP and Coordinator
|  |  | Nomination of gender and SGBV Focal point of the sector | X | X | X | X | Gender/SGBV FP and Coordinator
|  |  | Feedback mechanisms involve at least 50% of women and girls | X | X | X | X | Gender/SGBV FP and Coordinator
|  |  | Analyse disaggregated sector results on a quarterly basis and adapt activities to address gender inequalities | X | X | X | X | Coordinator and Gender Specialist
|  |  | Include tips and guidance for engaging with women's organisations as part of community based protection guidelines |  | X | X |  | Coordinator and Gender Specialist
|  |  | Focus on increasing number of women with legal residency | X | X | X | X | Coordinator
|  |  | Assess the protection of women and girls in Informal Tented Settlements, in particuar in Baalbek and Bekkaa |  | X | X

## Child Protection Work Plan 2022
2022 Child Protection Sector Workplan
Outputs | Key Priorities | Main Actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners
Please specify the link: - with your sector output and/or activity - or with the IS priority | List the key priorities identified | List the main actions that will be taken to ensure that each priority is addressed | Specify the timeline of implementation for each action |  |  |  | Specify who, within the coordination team (coordinator, IMO, core group…) is responsible for implementing this action | List the main partners involved in each activity
Output 1.3 Protection and legal frameworks are strengthened and implemented accurately and evenly to better respond to the protection needs of women, men, girls and boys in all their diversity. | Support the development of policies, procedures, training manuals, guidance to support the implementation of CP prevention and response programmes and strengthen application of existing laws and strategies | Review and update of tools/Guidance especially in regards to remote modality of implementation (including guidance for Hybrid approach) for both PSS and Case Management |  | X | X | X | CMTF and PSS committee | CMTF and PSS Committee members with key leading agencies including IRC, SCI, TDH-It, UNHCR
|  | Lead the efforts with MOSA on the review of the National SOPs for Child Protection case management, including the discussion around Alternative Care Guidance and BID |  | X | X | X | UNICEF, Sector coordinator with CG members | IRC, SCI, TDH-L, UNHCR
|  | Compile and adapt existing tools/guidance for remote Safe Identification and Referrals (SIR) of cases for high risk cases |  | X | X |  | CMTF and PSS committee | CMTF and PSS Committee members with key leading agencies including IRC, SCI, TDH-It, UNHCR
Output 2.1: Women, men, boys and girls in all their diversity have the information and resources to act upon informed decisions and participate in inclusive and accessible community spaces | Children's participation and engagement in community-based activities | Support the roll-out of guidance and training on safe identification and data collection on Children with Disability (CWD) involved in child protection activities. |  | X | X | X | Core Group members | UNICEF, SCI, TDH-L, IRC, UNHCR
| Quality and provision of Community Based Child Protection activities for children | Enhance/Promote more community-based child friendly spaces, and strengthen the capacity and engagement of community-based actors through Qudwa and other community-based initiatives. |  | X | X | X | Core Group members | UNICEF, SCI, TDH-L, Himaya, IRC, UNHCR
Output 2.2: Women, men, girls and boys in all their diversity are sensitised and engaged on issues of equality, SGBV and CP in their community. | Caregivers Support Programs | Review and update child protection activities for caregivers in order to enhance male caregiver engagement. |  | X | X | X | PSS committee | TDH-L, TDH-It, UNICEF, Plan int.
| Social and Behavioral Change “Qudwa” initiatives and activities, at the community level | Ensure standardization and inclusiveness (gender and disability) of guidance and SoPs on community-based initiatives |  | X | X | X | Core Group members | UNICEF
Output 2.3: Known, accessible and available complaint and feedback, protection against seual exploitation and abuse (PSEA) and child safeguarding mechanisms are in place. | Capacity building on PSEA | Organize training sessions on PSEA Core Principles and the PSEA SOPs for the CPWG members |  | X | X | X | PSEA network, GBV TF | CPWG members
|  | Inclusion of PSEA key messages in awareness raising activities (including on legal awareness or CP awareness, including in awareness sessions with caregivers) |  | X | X | X | PSEA network, GBV TF, PSS committee | CPWG members
|  | Support to the community consultations on the preferred channels to report SEA (outreach to possible participants in FGDs and KIIs and review of the findings) |  | X | X |  | UNICEF | SCI, TDH-L, Himaya, IRC
| CSG | Support the CPWG members (especially local partners) in developing and/or strengthening their child safeguarding policies. |  | X | X | X | Sector coordination, core group | SCI,Plan Int.
Output 3.1: Protection, CP and GBV services, including mental health and psychosocial services, are available, accessible, safe and informed by women, men, girls and boys in all their diversity. | Enhance quality and provision of Case Management (including through remote modality) | Coordination with the GBV TF on cases of children survivors of GBV and defining the management of these cases between GBV and CP partners |  | X | X |  | Sector coordination, CMTF, GBV TF | TDH-L, IRC, SCI, UNHCR
|  | Review and update SoPs on provision of Emergency Cash Assistance provided within the integrated CPCM, inclduding updating the unit cost based on current situation in country. |  | X | X |  | CMTF | IRC, SCI, TDH-It, Plan Int.
|  | Strengthen the system on alternative care arrangements, particularly with host families, including the identification of additional residential care facilities for emergency cases, and review/update the unit cost for Alt. care in the case management cost. |  | X | X | X | CMTF, UNICEF | IRC, SCI, TDH-It, UNHCR
|  | Advance the work on CPIMS and synchronizing with GBVIM for better reporting and analysis |  | X | X | X | CMTF, UNICEF | SCI, UNHCR
|  | Frame the discussion and strengthen the interventions around CAAC |  | X | X | X | CMTF, CAAC TF | TDH-L, SCI, UNRWA
| Continue prioritizing children at risk: chil labour, violence against children, CAAC,.. | Develop specific guidance and messages on the management of Child Labor cases, including WFCL and CAAC. |  | X | X |  | CMTF, CAAC TF | TDH-L, SCI, UNRWA
|  | Enhance the response to Child Labour including resource mobilization and coordination with other relevant sectors i.e. Education, Livelihood and Food Security sectors. |  | X | X | X | CMTF, sector coordination | TDH-L
| Enhnace quality provision of Focused non-specialized PSS services for children and Caregivers | Continuation of provision of FPSS for children and caregivers, including on specialized interventions such as child labour and CAAC |  | X | X | X | PSS committee, CAAC TF, CMTF | UNICEF, SCI, TDH-L, Himaya, IRC
|  | Support the roll-out of guidance and training on gender and disability inclusion for FPSS activities provided to children and caregivers. |  | X | X | X | PSS committee | UNICEF, UNHCR
|  | Constantly updating the FPSS curricula and adapting them to new protection shocks, including remote delivery modalities. |  | X | X | X | PSS committee | UNICEF, SCI, TDH-L, Himaya, IRC, UNHCR
| Staff well-being | Implement the recommendations from the survey on staff well-being and needs conducted last year, including development of videos and tips on staff self-care. |  | X | X |  | PSS committee | UNICEF, UNHCR
|  | Develop a training package on self-care for frontline workers. |  | X | X |  | PSS committee | UNICEF, UNHCR
Ensure effective Coordination of the CPWG | Inter-sectoral Coordination and referrals | Coordinate with the Education sector on mainstreaming CP interventions, including working with caregivers and enhancing safe identification and referrals in school settings/Non-formal education centers. |  | X | X | X | Sector coordination, IM | Key members of PSS committee and CMTF
|  | Follow-up, analyse and materialize the results of cross-sectoral indicators on prioritizing cases of child labor and street connected children across Livelihood and BA sectors. |  | X | X |  | Sector coordination | Key members of CMTF
|  | Enhance the coordination and collabration with the Health sector and national MHPSS TF, particularly in terms of tools/guidance notes development. |  | X | X | X | Sector coordinator, PSS committee | UNICEF, SCI, IRC
|  | In coordination with PRT sector, strengthen the gender and disabilities mainstreaming across all sectors. |  | X | X | X | Sector coordinator, PRT sector and GBV TF | UNICEF, SCI, IRC
| Data collection and CP monitoring | Review and update the data collection tools, including Real Time Monitoring and hotline tracking |  | X | X |  | IM and sector coordinator | SCI, IRC, Himaya, TDH-It, TDH-L
| Coordination with line ministries | Enhance coordination with MOSA, MoL and MEHE on the eradication of Child Labour, Violence against children and out of school children. |  | X | X | X | Mosa co-lead and sector coordination | CG members
| Internal PRT/SGBV/CP coordination on cross-thematic issues | Advance a whole of PRT core group discussions on key thematic areas: Child Labour, Child Marriage, CAAC, Persons with Disability | X | X | X | X | Core Group members of PRT/CP/SGBV | TDH-L
|  | Support the implementation of MoSA's strategy on Birth Registration | X | X | X | X | MoSA, Core Group members | UNICEF, UNHCR
| Gender | Gender in Humanitarian action training is conducted in 2022 at national and regional level |  | X | X | X | Coordinator and Gender Specialist
|  | Gender analysis two pager is drafted with support from Interagency Gender Specialist |  | X |  |  | Gender/SGBV FP, Coordinator and Gender Specialist
|  | All Child Protection assessments include gender specific questions and gender analysis | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Nomination of gender and SGBV Focal point of the sector | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Feedback mechanisms involve at least 50% of women and girls | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Analyse disaggregated sector results on a quarterly basis and adapt activities to address gender inequalities | X | X | X | X | Coordinator and Gender Specialist
|  | Start a reflection on how to strenghten girl's access to case management and increase percentage of fathers attending caregiver's sessions |  | X | X | X | Coordinator and Gender Specialist

## SGBV WP 2022
SGBV TF Work Plan 2022
Link to Protection Sector Strategy | Key Priorities | Main Actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Additional Comments
Output 1.2 & Output 1.3 | Support to national strategies | In close collaboration with the Health Sector and CMR TF, support the implementation of CMR Strategy including the capacity building program for health workers | x | x | x |  | SGBV TF | CMR Task Force, UNFPA, UNICEF |  | Capacity Building System Strengthening
|  | Support to the implementation of the Birth Registration Strategy | x | x | x | x | MoSA Co-Chair | UNHCR, UNICEF
|  | Support the implementation of 1325 NAP | x | x | x | x | NCLW | SGBVTASK FORCE, UNWomen, UNDP, unfpa
| Strengthening legal framework | Support implementation of Law 205/2020 (Harassment) and Law 204/2020 (Family Violence) and with awareness raising and information dissemination |  | x | x | x | Core Group | MOSA, KAFA, ABAAD, UNHCR, UNWOMEN, UNFPA | Raise awareness on these laws among judges to bar association to religious leaders, to SGBV partners. Collaborate with MEHE on introducing these two laws to teachers and children.
| Expansion and inclusiveness of SGBV TF membership | Support further engagement and collaboration with national institutional and academic actors (NCLW, ISF Gender Unit, MEHE) | x | x | x | x | SGBV TF | SGBV TF Co-Chair MOSA
|  | Expansion of membership of the SGBV TF and Inclusion of new members in the SGBV TF (including non traditional members, academic institutions, research centers, women-led organizations, LGBTIQ+ led organizations, organizations focusing on disability, organization supoprt patients of chronic illness) | x | x | x | x | SGBV TF | MOSA, NCLW
| Capacity Building of local/institutional Actors | Conduct training on gender and inclusion mainstreaming in capacity building programs and M&E activities | x |  |  |  | SGBV Core Group | UNICEF, UNFPA, MoSA
|  | Regularly share update on exisiting capacity building programs and share training material among memebrs |  |  | x | x | SGBV Core Group | UNICEF, UNFPA, HELEM
| Expansion of GBVIMS/ Safe and ethical data collection | Support the capacity building of new potential GBVIMS users |  | x | x |  | GBVIMS SC | SGBV TF | GBVIMS Coordinator provided technical support and assessed potential new users
Ouput 3.1 | Case Management | Development of join note on caring for child survivors in collaboration with CO and support related capacity building programs |  | x | x | x | GBV CG, IRC | UNFPA, UNICEF |  | Service Delivery
|  | Update of the Inter-Agency Guidance on Providing legal assistance for marriage registration in case of early marriages | x | x |  |  | SGBV Core Group | UNHCR, UNICEF, CP, PRT WGs
|  | Contribute to the development of the Protection Recurrent Cash Assistance (SOPs for GBV cases) | x |  |  |  | Core Group | UNFPA | In collaboration with Prortection Sector Cash WG
|  | Regularly update and disseminate the referral pathway, Service Mapping and the list of available hotlines | x | x | x | x | SGBV TF | SGBV Field WG Coordinators | Referral pathway updated on a quarterly basis
| Safe shelters | Develop note on safety options for survivors including description of all options for case workers | x |  |  |  | SGBV Core Group | ABAAD
| MH-PSS Technical Guidance | Collect lessons learned and good practice on different MHPSS conudcted by members | x |  |  |  | SGBV TF Chairs | SGBV TF
| Strengthening Legal Assistance | Regularly map existing specialized legal services for GBV survivors |  | x | x |  | Core Group | KAFA, ABAAD, CARITAS, UN WOMEN
| Frontline Staff Wellbeing | Collect and disseminate among members lessons learnt and good practices on how to ensure staff wellbeing during the pandemic and also in remote modality |  | x | x |  | SGBV TF Chairs
Ouput 2.2 | GBV Risk Mitigation and Mainstreaming | Update the GBV mainstreaming/risk mitigation plan that identifies key actors and responsibilities | x |  |  |  | Core Group | UNICEF, UNHCR |  | Risk Mitigation Mainstreaming
|  | Organize presentations on GBV risk mitigation in priority sectors and disseminate tip sheets on GBV risk mitigation/mainstreaming among LCRP sectors |  | x | x | x | SGBV TF | MoSA, UNICEF, UNFPA, UNHCR, UN WOMEN, WHO
|  | Train selected sector members on GBV risk mitigation and disseminate GBV mianstreaming tools in collaboration with Gender Focal Points |  | x | x | x | Core Group | MoSA, UNICEF, UNFPA, UNHCR, UN WOMEN, WHO
|  | Revise the safety audit tools and organize training sessions among SGBV partners |  | x | x |  | Core Group | UNICEF, UNHCR
|  | Regularly discuss at field and national level the findings of the safety audits |  |  | x | x | SGBV Field Coordinators | SGBV TF
Ouput 2.2 | Behavioral change and prevention | Collect and share lessons learned and good practices on BCC and community engament initiatives |  | x | x |  | SGBV Chairs | ABAAD, KAFA, IMC, DRC, IRC, UNRWA, UN Women |  | Prevention and Community Engagement
|  | Develop tip sheet on how to engae community, religiouos leaders and influencers |  | x | x |  | Core Group, UNICEF | UNFPA, MoSA
|  | Develop M&E Tools to measure impact of prevention activities |  |  |  |  | IRC, UNICEF | GBV CG
| Advocacy and Campaign | Coordinate the 16 Days of Activism Campaign |  |  | x | x | SGBV TF | UNHCR, UNFPA, UN Women
|  | Support ad hoc awareness and advocacy initiatives on specific Laws or topics |  | x | x | x | SGBV Co-Chairs | ABAAD, KAFA, UNICEF, UNHCR
Coordination, M&E and IM | Sector Coordination | Conduct regular monthly meetings of the SGBV TF and bimonthly meetinsg of the CG | x |  | x |  | Core Group | CP and PRT Core Groups |  | Coordination, M&E and IM
|  | Promote exchanges and collaboration with MHPSS TF |  | x |  | x | SGBV Co-Chairs
|  | Conduct joint meetings with CP on common areas of advocacy and programming (also at field level when possible) | x | x | x | x | SGBV TF Chairs | SGBV Field Coordinators
| Information and Knowledge Management | Draft and disseminate GBVIMS Reports to inform program and support advocacy points | x | x | x | x | GBVIMS SC | SGBV TF
|  | Regularly disseminate updates, studies, tools developed in country and at Global level with members (including regularly update the sector online folder) | x | x | x | x | SGBV TF Chairs | Core Group. IM Officer
|  | Review sector achievements and regularly discuss challenges and gaps with the SGBV TF members | x | x | x | x | SGBV Chairs | SGBV TF
| M&E | Disseminate assessments and evaluations conducted by SGBV partners |  | x | x | x | SGBV Chairs | Members of the TF
|  | Update the M&E Toolkit to simplify some of the tools and adapt them to the changing context (include tools to monitor and evaluate prevention activities and case management) |  | x | x |  | Chairs, IMO, IRC | SGBV CG