## GBV WG Work plan 2023
GBV WG 2023 Sector Workplan
|  |  |  | 2023 Timeline | [8 empty] | Status
Inter-Sector Priority & Mainstreaming Area | Key Priorities | Work plan indicators | Main Actions | Q1 | Q2 | Q3 | Q4 | Framework | Cross-Sector Support (Choose relevant sector/s with which you will work to achieve your priority) | Responsible Focal Person | Main Partners (Optional) | Additional Comments | Q1 | Q2 | Q3 | Q4
Inter-Sector Priority | Coordination | % of CSOs, CBOs, WL and Refugee led organizations, migrant led at national level WG Baseline: xx% Target: xx% | Facilitate monthly GBV WG meetings engaging all GBV actors in a meaningful and ensure flow of information | x | x | x | x | Joint | Protection sector and Child protection Sub sector | GBV WG co-chairs | UNFPA, UNHCR, MoSA
|  |  | Review membership list in line with the WG TORs for the WG and the Core Group and map member agencies/ through service mapping to analyze representation of CSOs, CBOs, WL and Refugee led organizations, migrant led, actively seeking to include national stakeholders and monitor presence in 2023 | x |  |  |  | Joint |  | GBV WG co-chairs | UNFPA, UNHCR, MoSA
|  |  | Review the different groups associated with or relevant for the GBV WG and establish a more formal focal point system with short tasks/ TORs (unless already available) to brief back to the group (current associated: GBV IMS TF, Core Group, CMR TF, Gender WG, LGBTIQ+ TF, etc.) | x |  |  |  | Joint |  | GBV WG co-chairs + IM | Core Group members with focal point responsibilities: CMR: Focal Points: Plan International (Afdokia), Abaad, active members: UNICEF, IMC L+ TF: May/ Nour (UNWOMEN) Gender: Monica (IRC), Sophie (UNHCR) Migrant: Julie (KAFA) Child Protection WG: Sophie (UNHCR), Intersos (Sawsan) Age and Disability: Samar (LUPD)
|  |  | Presenting good practices and innovative approaches on mitigation, prevention and response programs for peer learning at national and sub national level | x | x | x | x | Joint |  | GBV WG co-chairs | UNFPA, UNHCR, MoSA
|  |  | Involve and engage field-based GBV SWGs with presence of GBV SWG in all 4 regions at the national working group and a focal point system from GBV WG chairs in the different regions | x | x | x | x | Joint | Sub-national GBV SWGs, CP SWGs | GBV WG chairs at national and sub-national level | UNFPA, UNHCR, MoSA, NGOs selected as co-chairs
|  |  | Collect and disseminate needs analysis from the field-based SWGs and ensure field GBV risks and gaps are adequately reflected in the country-wide gap analysis | x | x | x | x | Joint | National and Field-based GBV SWGs | GBV WG chairs at national and sub-national level Partners to actvively share practices, studies and | UNFPA, UNHCR, MoSA
|  |  | Develop a thematic plan of priority subjects from March to December 2023 with involvement of sector members and circulate scheduled table | x |  |  |  | Joint |  | GBV WG co-chairs
|  |  | Develop a capacity builidng survey for the sector identifying technical support needs and relevant agencies with expertize on several specific subjects |  | x |  |  | Joint |  | GBV WG co-chairs | UNFPA, UNHCR, MoSA
|  |  | Harmonize capacity building interventions on GBV by collecting available training packages, creating a traing folder with different GBV related training modules and to review training material used by different agencies |  | x |  |  | Joint |  | IRC, UNFPA, UNHCR, UNICEF, other member agencies with relevant training | UNFPA, UNHCR, MoSA, IMC
|  |  | Roll-out a GBV Coordination Training for GBV WG coordinators and governmental actors in the field |  | x |  |  | Joint |  | UNFPA, UNHCR, MoSA | UNFPA, UNHCR, MoSA
| Advocacy and Campaigning | 40% of call for proposals from pool fund and key bilateral donors have included GBV as a priority | Prepare an advocacy note on the need and importance of GBV services including the need to ensure access for all different groups within the community (disability and people with diverse SOGIESC, etc.) |  | x |  |  | Joint | Protection sector | GBV WG coordinators, Protection WG, specific partners
|  |  | Train media on GBV safe reporting and circulate sector guidance |  | x | x |  | Joint | Comms Group | GBV WG coordinators, Protection WG, specific partners
|  |  | Mobilize resources by advocating with donors for increasing support of GBV as critical life saving intervention (including pool funding and bilateral donors) | x |  |  | x | Joint | ISWG | GBV WG coordinators, Protection WG, specific partners
|  |  | Engage and advocate with religious leaders around issues related to guardianship rights/ provision of nationality for women, child marriage |  | x |  |  | Joint |  | GBV WG coordinators, Protection WG, specific partners | Plan International & IMC
|  |  | Develop an advocacy note on key priority issues and challenges of the sector, including 2-3 core advocacy messages | x | x |  |  | Joint |  | KAFA, ABAAD: acces to legal services and justice; adolescent girls and access to education and impact on child marriage; access to information women from ifferent grups with specfiic needs; gender-sensitive legislation
|  |  | Mark, and celebrate relevant campaigns, including 16 days (25 November - 10 December), International day of girl child (11 October); WGwDs in International Day of People with Disability (IDPwD) is held on 3 Decemberl day | x | x | x | x | Joint | GBV WG | UNWOMEN, KAFA | Plan International LUPD
| Sector Situation Analysis | 100% of governorates covered with safety audit | Roll-out of 2023 Safety Audit in all locations with national level overview and analyze results for enhanced programming (Q2&3) and provide feedback community on results and findings (Q4) |  | x | x | x | Joint | Education, WASH, Shelter and MHPSS. Health and child protection to be prioritized | GBV WG national and sub-national coordinators
|  |  | Conduct GBV gap analysis and present to relevant stakeholders including affected women and girls |  |  | x |  | Joint | ISWG | GBV WG coordinators
| Monitoring & Evaluation | # of agencies trained reporting in a timely manner on AI across frameworks | Develop short guidance on GBV relevant outcome indicators and include systematically into intersectoral assessments where relevant and appropriate | x |  |  |  | Joint |  | GBV WG co-chairs + core group
|  |  | Review GBV WG M&E toolbox | x | x |  |  | Joint |  | GBV WG coordinators and core group
|  |  | Implement a contextualized client feedback survey for GBV Case management services into the monitoring framework and log frame and train sector members (roll-out the tool in Q1 and provide analysis on quarterly basis) | x | x | x | x | Joint |  | GBV WG co-chairs + core group
|  |  | Provide trainings on ActivityInfo for GBV WG members to enhance reporting in 2023 on LCRP and ERP to enhance reporting for sector | x |  |  |  | Joint | IM Unit (IS) | GBV Coordinators national level |  |  | Completed
|  |  | Coordinate with NCLW to ensure GBV partners report activities on 1325 NAP | x | x | x | x | Joint |  | MoSA, GBV Coordinators
|  |  | Conduct sector performance evaluation and disseminate as appropriate (GBV coodination survey on sector performance | x |  |  | x | Joint |  | GBV WG Coordinators national and sub-national level |  |  | Pending
| Preparedness and response | # of technical guidance notes produced or Referral Pathways are updated and circulated to sector members and at IA level | Update business contigency plan to adjust to different crisis, lessons learnt from recent experiences | x | x | x | x | Joint | Protection | GBV Core group |  |  | On-going
|  |  | Collect and disseminate lessons learnt and good practices on how to ensure staff wellbeing during the compounded crisis |  | x |  | x | Joint | MHPSS | GBV Core group
|  |  | Develop relevant guidance on safe shelters/safety options, with consultation with and participation of GBV actors. |  | x |  |  | Joint |  | Shelter agencies | GBV partners and CARITAS, ABAAD, KAFA, TABITA
|  |  | Finalize joint note on caring for child survivors in collaboration with CO and support related capacity building on the note (ToT) | x | x | x |  | Joint | Child protection | GBV WG | UNICEF, PLAN International |  | On-going
|  |  | Review current GBV referral pathways; regularly update and disseminate the referral pathway, ensure use of service mapping, including specialized services such as legal, CMR etc. and develop sectoral standard on referrals |  | x |  | x | Joint |  | GBV WG | Sub-national coordinators
|  |  | Map curent use of case management tools including GBVIMS+, proGres v4, and linked tools such as KOBO (client feedback survey) and roll of harmonized approaches on CM | x | x |  |  | Joint |  | GBV WG, GBV IMS TF Coordinate
| Behavioral change and prevention | Prevention strategy produced and endorsed correponding on impact and output indicators | Develop a GBV prevention strategy including male engagement, working with religious leaders and to foster longer term behavioral change |  | x | x |  | Joint | Protection, Child Protection, Education | GBV WG | IMC, PLAN INTERNATIONAL
|  |  | Map and collect good practices and update repository and Community of Practice (COP) under the Protection WG |  | x | x |  | Joint | Protection, Child Protection, Education | GBV WG co-chairs at national and sub-national level
Mainstreaming Area | Protection (including AAP, and referrals) | 100% of prioritized sectors have actions on gender and GBV included in their annual workplan | Undertake regular risk and gap analysis for stateless persons: outlining challenges in accessing services, increase awareness of legal framework and map/ ensure access to available services |  | x | x |  | Joint | Protection and PwD/ PwSN groups | GBV WG co-chairs at national and sub-national level
|  |  | Revise the intake form of the GBVIMS to highlight the age group and PwD | x |  |  | x | Joint | GBV IMS TF | GBV IMS TF
|  |  | Map feedback and complaints mechanisms of sector members and ensure all persons accessing GBV services and activities are aware of the complaints mechanisms |  | x |  |  | Joint | Protection | GBV WG co-chairs at national and sub-national level
|  |  | Organize/ conduct sectoral training on inclusion of PwD into GBV services (LUPD, Help age/ HI) | x |  |  |  | Joint | Protection and PwD/ PwSN groups | LUPD, Help age/ HI
| Age & Gender , Disability |  | Training/ sensitization of member agencies on LGBTIQ+ provided to all sector members (UN Women+ national NGOs working on advocacy aspects for SOGIESC/ LGBTIQ+) |  | x |  |  | Joint | Gender Working Group and IA Gender expert, Protection WG | L+ TF | Plan International, UNWOMEN, Helem
|  |  | Review inclusion of WGBM living with disabilities in GBV prevention and response plan and build capacity of GBV WG members on disability inclusion |  | x | x |  | Joint | Protection, Disability Task Force | LUPD | LUPD
|  |  | Ensure risk and gap analysis on GBV includes specific reference to adolescent girls and other specific risk groups including SOGIESC based on field-based information and data |  | x | x |  | Joint | Gender Working Group and IA Gender expert, Protection WG | L+ TF
| GBV risk mitigation across sectors |  | Prioritisation of specific sectors on GBV risk mitigation (Education, Shelter, Health, MHPSS and WASH) and define one or two ation points on GBV risk mitigation by sector | x | x | x | x | Joint | Farah (UNICEF), UNFPA, UNHCR, Education, WASH, Shelter and MHPSS. Health
|  |  | Develop a note on accommodation options for survivors and those at heightened risk of GBV, including SOGIESC - Shelter sector |  | x | x |  | Joint | Shelter sector, legal assistance TF
|  |  | Train the Gender and GBV Focal Points of different sectors to suppot in the monitoring of GBV risk mitigation |  | x | x | x | Joint | Education, WASH, Shelter and MHPSS. Health
| Conflict Sensitivity |  | Ensure GBV risk assessment includes analysis on potential harm and conflict sensitive aspects and ensuring all population groups are included in the analysis |  | x | x |  | Joint | Conflict sensitivity sector
|  |  | Support to partners in identifying specific risks or aspects on conflict sensitivity within their programs | x |  | x |  | Joint | Conflict sensitivity sector
| PSEA |  | Provide training for caseworkers on SEA victim assistance in the coaching program |  |  |  |  | Joint | PSEA coordinator and GBV WG chairs at national and sub-national level
|  |  | Ensure information on zero tolerance policy and reporting mechanisms are clearly visible in all service areas (GBV services and actviities) | x |  |  |  | Joint |  | Survey PSEA conducted
| Environment |  | During mapping of services ensure partners gradually use electronic filing systems to store information | x |  |  | x | Joint | GBV IMS TF, GBV WG co-chairs +environmental working group
|  |  | Advocating for use of evironmental friendly solution for WGSS and safe shelters |  | X | X | X | Joint