## Guidance
2021 LCRP Sector Workplan - Guidance
The 2021 AWP includes 2 tabs: 1. AWP based on your sector coordination role and Inter-Sector priorities: This tab should include a detailed work plan with key priorities and main actions that the sector will be responsible for through the coordination mechanism to foster a smooth implementation of the priorities on the ground. It includes a specific timeline for each action and should identify (1) who (within the coordination team) is responsible for implementing the main actions and (2) who are the main partners contributing to it. Please also consider the priorities/actions that are needed at the Inter-Sector level or with other sectors that will assist you to achieve the outcomes/outputs under your sector. For example, to ensure more vulnerable people have access to food we need to collectively look to strengthen the referral mechanisms at the inter-sector level; or to better achieve all outcomes/outputs we need to ensure that the research questions we have identified to the inter-sector as a priority under our sector are filled; or to ensure more conflict sensitive programming, we need to work with social stability sector and other sectors on a series of interventions. Please also feel free to include the activities/actions that will contribute to the coordination of your sector only. 2. AWP based on your sector logframe (optional): This tab should include the list of activities as listed in your logframe under each output and specify what are the timeframe, responsible and partners for each activity. Even if not mandatory we felt that it could still be useful for some sectors to fill it and have it available. 3. For both sections: As a lesson learnt from last year AWP process, we would like to highlight some key points to take into consideration during the process: • Be realistic: your AWP should not include too many activities, be selective. The timeline should be used to prioritize activities (for example, your sector won’t manage all activities in the first quarter). • When relevant, include cross-sectoral thematic priorities • Include mainstreaming aspects: conflict sensitivity, gender, AAP, PSEA, environmental impact, protection • Consider how you are planning to strengthen partnerships (e.g., with donors, national NGOS, civil society, development actors) • Include sustainability aspects of the workplan and how it will be linked to other frameworks and development discussions, including capacity building aspects • Consider how you are planning to make the link to national strategies • Consider how you are planning to flag issues and trends to the LCRP Inter-Sector • Specify how you are planning to monitor and analyze the current situation • Identify possible thematic dashboard to be developed during the year A solid draft should be submitted to the IA team no later than January 30th. We will need and use your draft AWP to prepare the discussions for the planning retreat. Based on the outcomes of the retreat, we will then ask you to finalize your workplan by February 10th.

## IS-coordination
2021 LCRP Sector Workplan - Sector Coordination / Inter-Sector priorities
2021 Timeline
Link to Sector Output and/or activity Or link to IS priority | Key Priorities | Main actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main partners (optional) | Additional Comments | Status Q1 | Status Q2
Please specify the link: - with your sector output and/or activity - or with the IS priority | List the key priorities identified | List the main actions that will be taken to ensure that each priority is addressed | Specify the timeline of implementation for each action |  |  |  | Specify who, within the coordination team (coordinator, IMO, core group…) is responsible for implementing this action | List the main partners involved in each activity |  | Monitoring of implementation to be done at the end of each quarter
Outcome 1 | Vulnerability Assessment of Syrian Refugees | Revision of analysis plan and questionnaire |  | X |  |  | BA Sector Coordinator, BA Core Group, | WFP, UNHCR, UNICEF |  | Completed
|  | Presentation of results and identifying needs |  |  |  | X | WFP, UNHCR | WFP, UNHCR, UNICEF
Output 2.1 and Output 2.2 | Winter Assistance | Lessons learned and preparations for 2021/2022 winter season. |  |  | X |  | BA Sector Coordinator
Outputs 1.1 and 2.1 | Monitoring the Survival and Minimum Expenditure Basket (S/MEB) | Monitoring the value of Survival Minimum Expenditure Basket with new price data | X | X | X | X | S/MEB technical group | UNHCR, WFP, SCI, RI |  |  | On-going
|  | Presentation of the S/MEB to the inter-sector | X | [6 empty] | Completed
Output 1.1 | Targeting for Multi-Purpose Cash Assistance | Discussion on/review of the 2021 targeting process | X | X |  |  | UNHCR, WFP possibly consulting BA Core Group | UNHCR, WFP
|  | Recalibration of the formula |  | X | X |  | UNHCR, WFP | UNHCR, WFP
|  | Communications Plan: development of communication plan in consultation with relevant stakeholders (BAWG, etc..) |  | X | X |  | UNHCR, WFP
|  | Interactive Targeting Sessions: Information sessions to partners on the modelling technique used |  | X |  |  | UNHCR, WFP
|  | Simulations of technical findings: dissemination of results (e.g. BAWG, FSWG, HCT, HoHA, ISWG, etc..) |  |  | X |  | UNHCR, WFP
|  | Update of the Redress / Appeals Strategy |  |  | X |  | UNHCR, WFP
|  | Operationalization: implementation of findings and conclusion of the exercise |  |  | X | X | UNHCR, WFP | UNHCR, WFP
Outputs 1.1 and 2.1 | Monitoring and Evaluation (M&E) Tools and Guidance | Update M&E tools and guidance for post distribution monitoring and outcome monitoring |  | X |  |  | BA Sector Coordinator
|  | Strengthening use of beneficiary feedback from M&E activities by fostering discussions around AAP systems and sharing trends to feed in to program design, decision making and Sector strategies |  | X | X | X | BA Sector Coordinator, Partners
|  | Regular review and update of research questions to the Inter-Sector |  | X | X | X | BA Sector Coordinator, BA Core Group
Output 1.1 | Updating the Protection Risk Assessment (PRA) | Conduct sessions at the field level to review and update PRA | X |  |  |  | BA Sector Coordinator, BA Field Coordinators |  |  |  | Completed
|  | Present results to Core Group to define priority risks, mitigation measures and develop monitoring plan |  | X | [6 empty] | On-going
|  | Present to working group |  | X | [5 empty] | Completed | On-going
|  | Monitor identified mitigation measures and actions |  |  | X | X
Inter-Agency Referrals | Strengthening Inter-Agency Referrals | Ensure regular presentation of referrals analysis at the field level | X | X | X | X | BA Sector Coordinator, BA Field Coordinators |  |  | On-going | On-going
|  | Communicate at Inter-Sector level details on services available through the Sector and define limitations | X |  |  |  | BA Sector Coordinator |  |  | Completed
|  | Set up a cash specific service mapping module for efficient referrals |  | X |  |  | BA Sector Coordinator, RIMS Coordinator, Inter-Agency IM
Output 1.1 | Ensuring complaints and feedback mechanisms (CFM) provide access to safe, accessible reporting for sexual exploitation and abuse (SEA) | Conduct quick assessment of available CFMs for SEA through BA partners |  | X |  |  | BA Sector Coordinator with support from Protection Sector Coordinator
|  | Identify partners that do not provide assess for reporting on SEA and provide solutions through the PSEA working group / Network to strengthen their prevention and response mechanisms |  | X |  |  | BA Sector Coordinator
|  | Support BA partners to review inter-agency minimum standard for complaints and feedback |  | X | X | X | BA Sector Coordinator, Protection Sector Coordinator
Coordination | Advocacy | Discussions around transfer values for multi-purpose cash assistance within the Core Group and the Basic assistance working group | X | X |  |  | BA Sector Coordinator, BA Core Group |  |  | On-going | On-going
|  | Continuous monitoring of key socio-economic indicators (exchange rate and consumer price index) | X | X | X | X |  |  |  | On-going | On-going
Output 3.2 | National Social Protection Strategy | Finalization and adoption of the National Social Protection Strategy and subsequent implementation plan | X | X | X | X |  | UNICEF, WFP |  | On-going | On-going
Mainstreaming | Conflict Sensitivity | Engage with Social Stability Sector to ensure cash implementation is carried out with a conflict sensitive approach Enhance access to humanitarian assistance in locations where conflict is reported | X | X | X | X | BA Sector Coordinator
| Protection, AAP | Ensuring modalities of assistance are inclusive to marginalized groups, monitoring of safe access to assistance, market and needs. Enhancing communication with communities, so that they are consistently updated on interventions of assistance |  | X | X | X | BA Sector Coordinator, key cash actors
|  | Mainstreaming Washington group questions in assessments and surveys to support disability inclusion |  | X | X |  | BA Sector Coordinator