## Sheet1
2021 Timeline
Sector Outputs | Activity | Sub-Activities | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Sector Focal Points | Status | Additional Comments | Legend of Initials:
Output 1.1 Temporary shelters (informal settlements and non-residential buildings) and residential shelters (for protection/referral cases) hosting vulnerable displaced populations are maintained at livable and safe conditions | Minor Repair of Non-Residential Substandard Building Technical Guidelines | 1- Launch TTC and call for expression of interest involving both BPB and LCRP partners to revise the existing technical guidance note. |  | x |  |  | SCI | TBD | CM/MR | Completed
|  | 2- Present an updated draft to the Core Group for endorsement. |  |  | x |  | NRC, SCI | TBD |  | Pending
|  | 3- Present the final document at the NSWG. |  |  | x |  | NRC, SCI | NRC, SCI |  | Pending
| Weatherproofing in Informal Settlements - Technical Guidelines | 1- Revise technical assessment questionnaire in accordance with recommendations from PDMs and field coordinators. | x | x |  |  | UNHCR | TBD | AA/MR | Completed
|  | 2-Develop awareness raising note on environmental concerns in collaboration with MoE. |  | x | x |  | UNHCR, MoE | TBD |  | Pending
|  | 3- Issue the finalized documents and technical assessment to Shelter sector partners. |  |  | x |  | UNHCR | TBD |  | Pending
|  | 4- Organize a technical training for partners that are implementing weatherproofing in informal settlements. |  |  | x |  | UNHCR | TBD |  | Pending
| Cash for Shelter Technical Guidelines | 1- Launch TTC and call for expression of interest involving both BPB and LCRP partners to revise the existing technical guidance note. |  | x |  |  | PCPM | UNHCR, PU-AMI, Solidarites, Concern | CM/MR | Completed
|  | 2- Share guidelines with Protection Sector for comments |  |  | x |  | Sector coordinators | TBD |  | Pending
|  | 3- Share guidelines with Core Group for comments |  |  |  | x | PCPM | TBD |  | Pending
|  | 4- Present find draft to MoSA for endorsement |  |  |  | x | PCPM, Core Group | TBD |  | Pending
| Stabilization of Buildings in Danger of Collapsing | 1- Consolidate work produced under the BPE response (possibly a checklist?) by UNHCT/ NRC/ Nusaned on determining buildings in danger of collapsing + inputs from UNHabitat's profiling assessment |  | x |  |  | UNHabitat. UNHCR | OEA, ?? | CM/MR | Pending
|  | 2- Share with OEA for comments |  |  | x |  |  | - |  | Pending
|  | 3- Present find draft to MoSA and after for WG for endorsement |  |  | x |  |  | - |  | Pending
| Collective Site Mapping Tool (COSIMA) | 1- Revice the COSIMA questionnaire |  | x |  |  | Field coordinators | TBD | DJ/AA | Completed
|  | 2- Scale up the mapping of collective sites across country and schedule training sessions for field staff on how to use the mapping tool. |  | x | x |  | IM, Field Coordinators | TBD |  | Pending
|  | 3- Produce updated collective shelters map and dashboard. |  |  |  | x | IM | TBD |  | Pending
Output 2.1: Residential shelters for vulnerable communities are upgraded as part of a multi-sectoral approach | Area Based Approach Guidelines and Coordination Structure | 1- Share ABA guidelines with core group and field coordinators for comments |  | x |  |  | UNHabitat | ACTED, Reach, IFRC, Field Coordinators | CM/MR | Ongoing
|  | 2- Present ABA TTC guidelines with representation from Social Stability, Protection and Water sectors) to the intersector. |  | x |  |  | UNHabitat | TBD |  | Pending
|  | 3- Contribute to developing ABA coordination structure and its respective ToRs setting roles and resposibilities for both national and field levels. |  |  | x |  | IS | TBD |  | Pending
|  | 4- Integrate ABA in the planning for 2022 and ensure reflection of activities in logframes of relevant sectors. |  |  | x | x | Sector coordinators | - |  | Pending
|  | 5- Share endorsed guidelines with NSWG and Interagency. |  |  | x |  | Sector coordinators | - |  | Pending
| Finalize Gap Analysis for residential and non-residential shelters | 1- Utilize VASyR to calculate population in need per district and compare against partners' confirmed targets and budget for 2021. | x |  | x |  | Sector coordinators | - | AA/FF | Ongoing
|  | 2- Share gap analysis and mapping of needs with shelter actors VASyR to calculate population in need per district and compare against partners' confirmed targets and budget for 2021. | x |  |  | x | Sector coordinators | - |  | Pending
| Upgrading of Residential Building - Physical Technical Assessment | 1- Revise the existing assessment form based on lesson learned from the BPB response | x |  | x |  | Field coordinators | NRC, SCI, UNHCR, UNHabitat | AA/DJ/HH/DF | Ongoing
|  | 2- Digitize the assessment and share with partners for piloting. |  |  | x |  | IM | TBD |  | Pending
|  | 3- Pilot and revise the shelter vulnerability assessment scoring accordingly. |  |  | x |  | IM | TBD |  | Pending
|  | 4- Final endorsement by Core Group and then by Sector members followed by a presentation at the NSWG. |  |  |  | x | IM, Core Group | TBD |  | Pending
| Protocol development on follow up to dangerous building identification | 1- Map government institutions involved in the indentification and response to buildings in danger to collapse | x | x |  |  | UNHabitat | TBD | CM | Completed
|  | 2- Draft protocol note on referral and follow up on buildings in danger to collapse identified as part of shelter assessments |  | x | x |  | Sector coordinators, UNHabitat | TBD |  | Ongoing
|  | 3- Share note with Core Group for approval |  |  |  | x | Sector coordinators, UNHabitat | TBD |  | Pending
|  | 4- Present note to MoSA for endorsement |  |  |  | x | UNHabitat | - |  | Pending
All Outputs | Protection mainstreaming | 1- Develop a protection risk assessment matrix for the shelter sector logframe |  | x | x |  | Sector coordinators | - | CM/AA | Ongoing
|  | 2- Intergrate findings of PRA in technical guidelines of relevant activities and PDM assessments |  |  | x | x | Sector coordinators and Core Group | UNHCR, Medair, Intersos, NRC, SCI |  | Pending
|  | 3- Conduct protection induction training for field shelter staff on identification and referral of protection cases |  |  |  | x | Protection Sector | UNHCR |  | Pending
| Shelter Manual encompassing all technical guidelines | 1- Compile all technical guidelines and terminology documents into one shelter manual for ease of reference |  | x | x | x | Sector coordinators | TBD | AA/FF | Ongoing
|  | 2- Publish guidance document online via Shelter Sector IA weblink |  |  |  | x | IM | TBD |  | Pending
| Gap/ Funding Analysis Platform | 1- Develop platform which automatically updates based on partner's implementation progress against critical needs identified through VASyr and partners assessments. | x | x |  |  | AA | - | AA/MS | Ongoing
|  | 2- Present platform at the NSWG. |  | x | x |  | AA | - |  | Pending
| Contingency Planning | 1- Develop response scenarios and planning figures for the 6 risks identified. |  | x |  |  | Sector Coordinators | - | AA/CM | Completed
| Housing Land and Property Technical Guidelines | 1- Launch task force with members from the shelter and protection sectors assessment to revise the HLP guidance document that was developed under the BPE response. |  |  | x |  | UNHabitat and NRC | - | AA/CM | Ongoing
|  | 2-Share updated draft with the core group for endorsement. |  |  |  | x | Sector coordinators | - | AA/CM | Pending
|  | 3- Share final draft with MoSA for final endorsement. |  |  |  | x | Sector Coordinators | - | AA/CM | Pending

## Sheet2
Status
Completed
Pending
Ongoing

## Sheet3
Task