## 2015 Sector WP
Basic Needs Sector Workplan 2015
Key Areas of Work |  | Activities | Expected Output | J | F | M | A | M | J | J | A | S | O | N | D | April Status | August Status | Comment/ Rationale
A. Basic Needs Working Group Workplan | VAF | Sector Tree Finalization | [13 empty] | completed | completed
|  | Validation of criteria and decision trees | [13 empty] | started | started
|  | Operationalization | [13 empty] | not started | pending
| Reporting | Indicator Formulation / Validation | [13 empty] | completed | completed | bar: J to F; A; A; D
|  | Monthly reporting (by 8th of each month) | [13 empty] | started | started
|  | Quarterly review of reporting gaps across sector at BNWG level | [15 empty] | *Olivia requesting inclusion
|  | Development of products for local/regional meetings | [13 empty] | not started | not started | bar: A to J; A; D
|  | Formulate impact measurement metholodgy | [13 empty] | not started | not started | bar: A; J to S; D
| Internal procedure | Strategy / Workplan workshop | [13 empty] | completed | completed | Available on Information portal
|  | Terms of Refernce formulation | [13 empty] | completed | completed | Available on Information portal
|  | Develop repository of Basic Needs- related SOPs and standards | [13 empty] | completed | completed | Available on Information portal
|  | Communications protocol | [13 empty] | started | started
|  | Mid-year review of structure and ToR | [13 empty] | not started | completed
|  | Mid-year survey of added value and suggestions | [13 empty] | not started | completed
|  | Refining ToR for committees in camps | [13 empty] | started | started | Za'atari Yes, Azraq No
| Operational Support | Develop a cash assistance "duplication checker" similar to winterization module | [13 empty] | not started | not started | Minimum standards first | bar: A to M; A; D
|  | Formulat standard approach regarding identification and assistance towards JOR beneficiaries | [13 empty] | not started | started/ pending | MoSD participation required via MEB standarisation TF | bar: A to J; A; D
|  | Revisit standardization of NFIs (camp and non-camp) | [13 empty] | not started | started | To be discussed by MEB Standardisation TF | bar: A to J; A; D
|  | Minimum standards (also informed by MEB formulation) | [13 empty] | started | started | To be discussed by MEB Standardisation TF | bar: M to J; A; D
|  | Formulation of processes related to calls for proposals (HIP, ERF, BPRM) | [13 empty] | started | started | bar: J; A to M; A; D
B. Cross-Sector Collaboration | GAD | Development of joint (multi-agency) gender impact assessment | [13 empty] | not started | started | Gender Advisor led via the Jordan Refugee Inter-agency task force sector gender focal point network
|  | Implementation of action plan (cf. gender focal point group) | [13 empty] | not started | started | The Jordan Refugee Inter-agency Task Force Sector Gender Focal Point Network
| MEB | Faciliatet setup of TF under ISWG | [13 empty] | completed | completed | bar: M to A; A; D
|  | Contribute to MEB formulation | [13 empty] | started | completed | MEB validated June 2015 | bar: M to A; A; D
| C&V Support | Define potential and limits of monetization (builds on MEB findings) | [13 empty] | not started | not started
|  | Support synergies, incl. joint programming and delivery mechanisms | [13 empty] | not started | not started
| Winterization TF | Lead the conclusion of 2014-5 winterization | [13 empty] | started | started | bar: J to A; A; D
|  | Initiate inter-sector preparation and coordination of 2015-6 winterization | [13 empty] | not started | started | To start September | bar: A; J to D
| Protection | Referral pathways | [13 empty] | not started | not started
|  | Service mapping (ActivityInfo) | [13 empty] | not started | completed | OC updated all network referral mechanisms spanding all partners, sectors and locations
|  | Stock-taking of PSEA in place or in elaboration | [13 empty] | not started | completed | OC Updated referral system including PSEA visibile via Service Advisor online dashboard
|  | Coordination on urgent cash assistance | [13 empty] | started | started | part of 3RP formulation, review and SOPs (also relates to Health)
|  | Stock-taking of complaints mechanisms and investigation procedures | [13 empty] | not started | not started
|  | Livelihoods | [13 empty] | started | started
| Shelter | Provide input on cash-for-rent guidance | [13 empty] | completed | completed | bar: F to A; A; D
|  | Continuous coordination on cash for rent (conditional vs unconditional) | [13 empty] | started | started | Also happening in the context of the MEB | bar: J; M to M; J to S; N to D
| JRP | Facilitate participation of relevant ministry | [13 empty] | completed | started | MoSD participating
|  | Provide regular updates on connection and integration into JRP | [13 empty] | started | started
| WASH | Coordinate on which sector is to manage hygiene kits | [13 empty] | not started | not started | current division is artificial and relates to the 2012 division of labour
|  | Coordinate on cash-for-WASH (cash for water) activities | [13 empty] | not started | not started

## 2016 Sector WP
Basic Needs Sector Workplan 2016
Key Areas of Work |  | Activities | Ownership | J | F | M | A | M | J | J | A | S | O | N | D | January Status | April Status | August Status | December Status | Comment/ Rationale
A. Basic Needs Working Group Workplan | Sector Coordination | JRP/3RP PSS submissions 2016 Sector Programme Planning (Planning early) | All partners | [12 empty] | not started
|  | Donor Coordination - future year ahead priorities (2016 - 2017) | Sector WG | [12 empty] | not started
|  | Programming development- Consortium bids / multisector / multipurpose | Sector WG /ISWG/ partners | [12 empty] | not started
|  | Common Cash Fund | Volker / partners | [12 empty] | not started
|  | Winterization Activity Planning 2016-17 begins with PSS submissions based on LL 2015-16 | All partners | [12 empty] | not started
|  | Data Sharing MOUs in place / onboarding of partners | All partners / UNHCR / DAG | [12 empty] | started
| VAF | Sector Tree Re-review and Finalization | [13 empty] | started
|  | Validation of criteria and decision trees | [13 empty] | started
|  | Operationalization | [13 empty] | not started
| Reporting | ActivityInfo Reporting | All partners | [12 empty] | ongoing
|  | RAIS Assistance and Winterization Reporting | All partners | [12 empty] | ongoing
|  | Quarterly review of reporting gaps across sector | UNHCR Coord | [12 empty] | started
|  | Development of products for local/regional meetings | UNHCR Coord | [12 empty] | not started
|  | Formulate impact measurement metholodgy | Sector WG | [12 empty] | not started
| Internal procedure | Strategy /2016 BN Workplan endorsement | [13 empty] | not started
|  | Communications protocol | [13 empty] | started
|  | Mid-year review of structure and ToR | [13 empty] | not started
|  | Mid-year survey of added value and suggestions | [13 empty] | not started
|  | Refining ToR for committees in camps | [13 empty] | started |  |  |  | Za'atari Yes, Azraq No
| Operational Support | Develop a cash assistance "duplication checker" similar to winterization module | UNHCR Coord/ DAG | [12 empty] | not started |  |  |  | Minimum standards first
|  | Formulat standard approach regarding identification and assistance towards JOR beneficiaries | [13 empty] | started |  |  |  | MOSD JOD beneficiary taskforce
|  | Revisit standardization of NFIs (camp and non-camp) | [13 empty] | not started |  |  |  | Assistance types revisited
|  | Minimum standards (also informed by MEB formulation) | [13 empty] | started
|  | Cash for Work Module development | UNHCR Coord/ DAG/ NBWG
|  | Formulation of processes related to calls for proposals (HIP, ERF, BPRM) | [13 empty] | started
B. Cross-Sector Collaboration | GAD | Development of joint (multi-agency) gender impact assessment | [13 empty] | not started |  |  |  | Gender Advisor led via the Jordan Refugee Inter-agency task force sector gender focal point network
|  | Implementation of action plan (cf. gender focal point group) | [13 empty] | not started |  |  |  | The Jordan Refugee Inter-agency Task Force Sector Gender Focal Point Network
| MEB | Continued Coordination of TF under ISWG | MEB TF | [12 empty] | ongoing
|  | Readdress approach to sizing levels of assistance for multipurpose multidimensional programming | MEB TF | [12 empty] | started
|  | Development of guidance documenting multipurpose approach | MEB TF | [12 empty] | started
|  |  | MEB TF | [12 empty] | started |  |  |  | MEB validated June 2015
| C&V Support | Define potential and limits of monetization (builds on MEB findings) | MEB TF | [12 empty] | started
|  | Support synergies, incl. joint programming and delivery mechanisms | MEB TF | [12 empty] | started
|  | Cash and voucher usage ECA/UCA | ECA/UCA TF Sector Level | [12 empty] | not started
| Winterization TF | Lead the conclusion of 2015-6 winterization | [13 empty] | started
|  | Initiate inter-sector preparation and coordination of 2016-7 winterization | [13 empty] | started
| Protection | Referral pathways development RAIS | UNHCR Coord/ DAG | [12 empty] | started
|  | Referral pathways network coordination | UNHCR Coord/ DAG | [12 empty] | started |  |  |  | Central, Mafraq and Irbid
|  | Service mapping (ActivityInfo) | All partners | [12 empty] | started
|  | Stock-taking of PSEA in place or in elaboration | [13 empty] | not started
|  | ECA/UCA guidance, methodology | ECA/UCA TF Sector Level | [12 empty] | not started
|  | Enhancing coordination on UCA/ECA | ECA/UCA TF Sector Level | [12 empty] | not started
|  | Stock-taking of complaints mechanisms and investigation procedures | [13 empty] | not started
|  | Livelihoods | [13 empty] | started
| Health | Continuous coordination on cash for health | [13 empty] | started | bar: J to A
| Shelter | Continuous coordination on cash for rent (conditional vs unconditional) | [13 empty] | started |  |  |  | Also happening in the context of the MEB
| JRP/JORIS | Facilitate participation of relevant ministry 2016-17 | [13 empty] | not started |  |  |  | MoSD participating
|  | JORIS upgrade and facilitating approvals via line ministries | [13 empty] | not started
|  | Provide regular updates on connection and integration into JRP | [13 empty] | started
| Intersector Linkages | Consolidate sector workplans to idenitfy linkages | ISWG / Sector | [12 empty] | not started
| WASH | Coordinate on which sector is to manage hygiene kits | [13 empty] | not started |  |  |  | current division is artificial and relates to the 2012 division of labour
|  | Coordinate on cash-for-WASH (cash for water) activities | [13 empty] | not started

## 2016 Zaatari WP
Objective |  | Activity |  | Time Frame/Month | [24 empty] | Responsible Party | Reporting/ Documentation | Related Indicator
|  |  |  | Jan | Feb | Mar | April | May | June | July | Aug | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  | Dec.
[12 empty] | 6-10 | 13-17 | 20-24 | 27-1 | 4-8 | 11-15 | 18-22 | 25-29 | 1-5 | 8-12 | 15-19 | 22-26 | 29-3 | 6-10 | 13-17 | 20-24 | 27-31
1 | Implement Community Gatherings | 1.1 | Conduct group discussions in field, obtain discussion points on upcoming Community Gathering topics, and invite refugees to Gatherings | [25 empty] | IRD Community Mobilizers
|  | 1.2 | Invite district partners and partners relevant to selected topic for Gatherings and provide them with summary discussion points | [25 empty] | IRD ComMob Assistant Coordinator | Daily Reports
|  | 1.3 | Implement Gathering, address one topic selected by refugees, determine action points | [25 empty] | IRD Community Mobilizers, UNHCR, district partners, relevant partners | Gathering Minutes | # of Gatherings implemented; # of beneficairies attending Gatherings
|  | 1.4 | Prepare and distribute Gathering minutes and Communique to concerned partners | [25 empty] | IRD Community Mobilizers, IRD ComMob Assist. Coordinator, UNHCR Mass Media | Gathering Minutes
|  | 1.5 | Follow-up on action points from Gatherings | [25 empty] | IRD Community Mobilization Coordinator, Assist. Coordinator, Mobilizers, other relevant partners | bar: Time Frame/Month Sept. 11-15 to Time Frame/Month Sept. 27-31
2 | Disseminate Key Information to Syrian Community | 2.1 | Identify priority outgoing messages to disseminate to community on a weekly or biweekly basis; topics include outcomes of Gatherings, UNHCR/partner campaigns, IRD campaigns | [8 empty] | Time Frame/Month Sept. 4-8: new method! | IRD Community Mobilization Coordinator | Daily Reports, Weekly Reports
|  | 2.2 | Dissemination of priority outgoing messages in the community and collection of feedback points from refugees on this messaging | [8 empty] | Time Frame/Month Sept. 4-8: new method! | IRD Community Mobilizers
|  | 2.3 | Post and disseminate written materials concerning priority outgoing messages in community | [25 empty] | IRD Community Mobilizers | written materials
3 | Implement Mapping, Assessment, and Recruitment Tasks | 3.1 | IWWM Project: Mapping of vulnerable households for assistance in connnection to wastewater system | [25 empty] | IRD Community Mobilizers | Daily Reports, Weekly Reports
|  | 3.2 | IWWM Project: Mapping of household wastewater outlets to assist in design of unit systems | [25 empty] | IRD Community Mobilizers | Daily Reports, Weekly Reports
|  | 3.3 | Conduct internal and external field assessments as requested | [25 empty] | IRD Community Mobilizers | Daily Reports, Weekly Reports
|  | 3.4 | Assist in recruitement of volunteers and participants for IRD component and partner NGO programs, as requested | [25 empty] | IRD Community Mobilizers | Daily Reports, Weekly Reports
4 | Develop Capacity of Staff | 4.1 | Training on Meeting Minutes for Community Gatherings | [25 empty] | IRD Community Mobilizers, Trainer: IMU Coordinator
|  | 4.2 | Persons with Impairments/Disability - Awareness Training and Specialized Inclusion Training | [25 empty] | IRD Community Mobilizers, Trainer: Handicap International
|  | 4.3 | Training on Facilitation and Time Management of Community Gatherings | [25 empty] | IRD Community Mobilizers, Trainer: UNHCR? | bar: Time Frame/Month Sept. 4-8
|  | 4.4 | Collaboration and organizing coorespondance and sit each duties for both IRD community mobilizers and UNHCR district focal points | [25 empty] | IRD Community Mobilizers, Trainer: UNHCR? | bar: Time Frame/Month Sept. 4-8
5 | Co-lead Community Mobilization Working Group | 5.1 | Co-chair Community Mobilization Working Group, managing communications and facilitation of bi-weekly meetings | [25 empty] | IRD Community Mobilization Coordinator | Meeting Minutes
|  | 5.2 | Coordinate interagency cooperation on Community Mobilization initiatives and messaging campaigns | [25 empty] | IRD Community Mobilization Coordinator
|  | 5.3 | Discuss the messages being disseminiated in the camp to identify and assign the sutiable community mobilization channel\ tool to destribute them | [25 empty] | IRD Community Mobilization Coordinator
|  | 5.4 | Organize and develop community gatherings structure and future plans with the group members | [25 empty] | IRD Community Mobilization Coordinator
4 | Assist in Caravan Distribution Process | 4.1 | Verify cases requesting caravans through UNHCR criteria | [25 empty] | IRD Community Mobilizers | Daily Reports
|  | 4.2 | Identifying eligible cases and re-distribution of return office caravans | [25 empty] | IRD Community Mobilizers | Daily Reports
|  | 4.3 | Distribution of fixed caravans according to UNHCR lists | [25 empty] | IRD Community Mobilizers | Daily Reports
Note on D8: Marzieh Goudarzi: started this in Oct, so we have time to plan our role in this process
Note on D10: Marzieh Goudarzi: this refers to the new messaging system that we will implement, though we did implement information dissemination to earlier as well