| Name | TF | Meeting Date | 21 August 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 9:00 |
| Co-Chairs | Hussein Salem (MOSA), Josep Zapater (UNHCR) | Meeting Duration | 2 hour |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |
| Purpose of Meeting | Follow-up and next steps on the Arsal, Litani and Maqne situations |

Meeting

Meeting agenda

- General updates and follow up from last meeting

- Rubble management

- Issue of figures in Arsal

- Shelter assistance

- Winterization in Arsal

- Other situations in the Bekaa: dismantlement, Maqne, Litani

Summary of discussions and decisions - Arsal

Main updates

- There is good progress on shelter delivery and also rubble removal. Figures below, or coming this Friday.

- All sectors provided sector gap analysis. Main gaps (in particular those quantified – shelter, food for child friendly spaces, cash assistance for winter) shared with donors by RC / HC. Main gaps still persisting. The need for child friendly spaces to diminish only after beginning of the schoolyear.

- Intersector to undertake an assessment on how dismantling has affected the vulnerability of affected families in Arsal, in particular from the viewpoint of debt, protection / negative coping mechanisms, and mental health.

Priorities before winter

- Addressing the impact of the dismantlement situation on the protection, vulnerability and mental health of refugees,

- Developing a timely action plan for shelter winterization response, as well as fire prevention, taking into account the changing situation due to dismantlement,

- Wrapping up the current operation, in particular in terms of shelter assistance, and clarifying figures,

- Emergency preparedness for winter.

Main decisions

- Intersector to conduct assessment on the impact of the dismantlement situation on the protection, vulnerability and mental health of refugees,

- Shelter sector to develop an action plan for shelter winterization response, ready first week of September,

- MOSA and UNHCR to organize Arsal winter preparedness meeting second week of September.

Detailed action points – Arsal situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Conduct assessment on the impact of the dismantlement situation on the protection, vulnerability and mental health of refugees | Implemented by FPS – under direction of the Intersector | End September |  |
| Provide comments to research questions for the a/m assessment | Intersector | 21 August 2019 |  |
| Share figures on update on rubble removal | Shelter sector | 21 August 2019 |  |
| Organize a follow-up meeting on rubble with all involved | URDA to fix date | 28 August 2019, tentatively |  |
| Coordinate bilaterally SGBV – mental health, so that SGBV partners are aware of availability of mental health services | SGBV & Health sectors | ASAP |  |
| Coordinate bilaterally CP – Education, as regards availability of non-formal education mechanisms | CP and Education | ASAP |  |
| Coordinate bilaterally Protection – MOSA, on issues of relocation needs | MOSA and Protection | Ongoing |  |
| Finalize winterization assessment | PCPM | End September |  |
| Prepare, by the first week of September, a shelter action plan focusing on winterization and fire prevention, taking into account: Installation of fire breaks, Other fire prevention mechanisms, including training, sensitization and provision / maintenance of extinguishers, Site maintenance, taking into account PWSN, Winterization, PWSN, Information mechanisms for refugees. The action plan will be developed on the available results of the winterization assessment by the time of planning. It will explain the articulation and timing of all elements above, as well as adapt to different scenarios of dismantling. | Shelter – with assistance from Protection for information to communities. | 1st week of September |  |
| Organize Arsal emergency cell meeting on winter preparedness | MOSA and UNHCR (Snr field coordinator) | 2nd week of September |  |
| Share status of rubble removal and shelter distributions per site | UNHCR (Snr field coordinator) | 21st of August |  |
| Re-share instructions for EOS usage | Shelter | ASAP | ` |
| Regularly update EOS | all | Ongoing |  |
| Share corrected EOS figures on the dismantlement situation | UNHCR (Snr field coordinator) | Friday 23rd of August |  |

Updates on other situations

- On the Litani situation, pilot relocation is awaiting approvals from the Ministry of the Environment.

- On the Maqne situation, site approval has finally been granted by Mayor and Governor [this update came shortly after finishing the meeting].

21 August 2019

# Text boxes

Emergency TF – Minutes of Meeting