## IS-Coordination
2022 LCRP Water Sector Workplan - Sector Coordination / Inter-Sector priorities
2022 Timeline
Link to IS Priority/Mainstreaming Area Or link to IS priority | Key Priorities | Main Actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners (optional) | Additional Comments | Status
Coordination | Sector Coordination Efforts | Update the drive folder to include all Tools and SOPs for the Water Sector | X |  |  |  | Sector IM/Sector Co-lead
|  | Conduct 5W of WASH projects in permanent locations with a focus on solarization | X | X |  |  | Stabilization TG
|  | Develop Sector Strategic Operational Framework |  | X | X |  | Sector Coordinator/Core Group
|  | Ensure cross attendance and participation in the other sector's working groups and provide important WASH sector updates. | X | X | X | X | Sector Coordinator/Sector Co-lead
| Sector Advocacy Efforts | Continue to advocate for Water Establsihment support | X | X | X | X | Sector Coordinator/Sector Co-lead
|  | Continue to advocate to move to more cost-effective services in ISs | X | X | X | X | Sector Coordinator/Sector Co-lead
| Inter-Sector Coordination | Strengthen collaboration with Energy Sector on Solarization | X | X | X | X | Sector Coordinator/Sector Co-lead
|  | Strenghten collaboration with Social Stability Sector on Waste Management in ISs - suggesting support to municipalities also | X | X | X | X | Sector Coordinator/Sector Co-lead
|  | Strenghten collaboration with Health sector on water-borne diseases and follow up on outbreaks where WASH conditions might be the causes. | X | X |  |  | Sector Coordinator/Sector Co-lead
| Reporting | Keep ActivityInfo reporting updated | X | X | X | X | Sector Coordinator/Sector Co-lead
|  | Keep the Inter-Sector service mapping updated | X | X | X | X
|  | Produce quarterly reporting dashboards | X | X | X | X
Need assessments | WASH Vulnerability mapping for permanent locations | Analyze VM Results and Plan for validation and update with Partners | X |  | X | X | Sector IM/Sector Coordinator/Sector Co-leadr/Core Group
|  | Discuss the updated map with the sector stabiliztaion thematic group |  | X |  |  | Sector IM/Sector Coordinator/Sector Co-lead/ Stabilization Thematic Group
|  | Develop additional criteria by the sector stabilization and Safe Water Access thematic group to reflect the WASH vulnerability |  | X |  |  | Sector IM/Sector Coordinator/ Safe Water Access Thematic Group
| WASH Assessment Platform (WAP) for ISs | Collect and analyze new Sweep of WAP data | X | X |  |  | Sector IM/Sector Coordinator/Sector Co-lead
| KAP survey | Revision of existing KAP tools in the sector and identify a standard tool to be adopted for all partners | X | X |  |  | Comunity Mobilzation Thematic Group
Mainstreaming Area | Gender, SGBV and Youth mainstreaming | Strenghten Collaboration with Gender Specialist and SGBV Task Force on safe access to WASH facilities for women and girls, including capacity building actions for 2022 for LCRP partners. Assess SGBV risks and put in place SGBV risk mitigation measures. | X | X | X | X | Sector Coordinator/Sector Co-lead/Community Mobilization Thematic Group
| Environment Mainstreaming | Coordinate with ETF on (i) environmental complaints, (ii) dentifying key actions to protect riparian ecosystems from ISs pollution sources, (iii) desludging mechanisms and reporting (how much, where from, where to? etc.) | X | X | X | X | Sector Coordinator/Sector Co-lead/Sanitation Thematic Group
|  | Conduct regular trainings on the use of the environmental marker and other safeguards rules and regulations, and on Solid Waste Management, WW management, irrigation with treated wastewater, etc. |  | X
|  | Assess impacts of ITS on agricultural lands |  |  | X | X |  | not admissible
| Conflict Sensitivity | Develop SOP on "Conflict management" for WASH actors with Municipalities and Landlords | X | X |  |  | Sector Coordinator/Sector Co-lead/CS Mainstreaming FP
|  | Quarterly updates on the Tensions Landscape at WASH Working Groups Thematic discussions with Conflict Sensitivity focal point Training partners on conflict sensitivity |  | X | X |  | Sector Coordinator/Sector Co-lead/ CS Mainstreaming FP
| Gender | Gender in Humanitarian action training is conducted in 2022 at national and regional level |  | X | X | X | Coordinator and Gender Specialist
|  | Gender analysis two pager is drafted with support from Interagency Gender Specialist |  | X |  |  | Gender/SGBV FP, Coordinator and Gender Specialist
|  | All WASH assessments include gender specific questions and gender analysis | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Nomination of gender and SGBV Focal point of the sector | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Feedback mechanisms involve at least 50% of women and girls | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Analyse disaggregated sector results on a quarterly basis and adapt activities to address gender inequalities | X | X | X | X | Coordinator and Gender Specialist
|  | Menstrual hygiene management: consultations with women and girls, conduct MHM awareness sessions, distribution of menstraul hygiene kits | X | X | X | X | Water Sector Partners
|  | Organise a meeting to present results of the mapping of women's organisations and how to engage them for assessments and implementation |  |  | x |  | Coordinator and Gender Specialist
| Protection | Strengthen complaint and feedback in the sector; a. ensure partners have clear messages to communicate to beneficiaries about available channels; b. ensure regular trend analysis in WG; promote best practice and share the IA CFM guidelines with partners |  | x | x |  | Community Mobilization Thematic Group

## Logframe Activities
Example: 2022 LCRP Health Sector Workplan - Logframe Activities
2022 Timeline
Sector Output | Key Activities | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Additional Comments | Statute
Outcome 1: Strengthen national, regional and local public institutions’ capacities to deliver improved public policies, goods and services (water and sanitation). "
Output 1.1: Develop institutional governance to adopt key water strategies. | Development and adoption of a national water quality monitoring plan |  |  |  |  | MOEW/WEs
| Development and adoption of a national ground water resource monitoring plan |  |  |  |  | MOEW/WEs
| Develop a plan for Digitalization of WEs and MOEW databases |  |  |  |  | MOEW/WEs
Output 1.2: supporting water institutions operations and building their capacity. | Provision of Equipment/Provision of in-kind assisstance to WEs and training support Ministry of Energy and Water and Water Establishment | X | X | X | X | UNICEF
| Assist in developing Water SAFETY PLAN at site level including training of partners and WEs Staffs |  |  | X | X | Safe Water Access Thematic group
Outcome 2: More vulnerable people in Lebanon are using safely managed drinking water and sanitation services whilst reducing health and environmental risks and improving water quality by increasing the proportion of wastewater that is safely treated.
Output 2.1: The most vulnerable in hosting and displaced communities have access to sufficient quantity of quality, reliable and equitable water and wastewater services | Implementation of the Sanitation Plan in ISs Scale up innovations and pilot programmes in water and wastewater management for temporary sites | X | X | X | X | Sanitation Thematic Group
| Construction and maintenance of Water and Sanitation facilities in permanent locations following the NWSS | X | X | X | X | Sectors Partners
| Provision of WASH services in temporary locations including Construction and maintenance of WASH facilities, Water Trucking and Desludging | X | X | X | X | Sectors Partners
| Training on developing Water SAFETY PLAN at Informal Settlement level including training of partners and WEs Staffs |  | X | X |  | Safe Water Access Thematic Group
| Implement CASH for WASH activities | X | X | X | X | Sectors Partners
Output 2.2- Displaced and host communities adopt sustainable and responsible social and WaSH behavior. | Develop a clear Behavior Change strategy in ISs and CS (includes first a study) integrating WaSH, Health, SoST and protection. |  | X |  |  | Community Mobilization Thematic Group, Sector Partners
| Perform pre and post KAP survey |  | X |  | X | Community Mobilization Thematic Group, Sector Partners
| Conduct Awareness sessions in ISs following the behavior change strategy | X | X | X | X | Community Mobilization Thematic Group, Sector Partners